## Slide 1
QUARTERLY BUSINESS REVIEW · CONTOSO · Q2 2026
Agent and governance work advanced; commitments and connectors slipped
Evidence window 1 April - 30 June 2026, with carry-forward status read through 7 September 2026
4
5
2
Active workstreams
High-priority items open
Data connectors flagged
Source: Outlook mail, Teams chats, calendar and SharePoint files, 1 Apr - 7 Sep 2026
Notes: Quarter reviewed: Q2 2026 (1 Apr - 30 Jun), with carry-forward status read through 7 Sep 2026. Four active workstreams: Zava S2P agent platform, AI governance (ZAVA/ZAG), ERP cloud procurement, marketing GTM. Five high-priority open items and two flagged connectors come from the 6 Sep 2026 task digest.

## Slide 2
Agent platform and enablement delivered; governance, ERP award and marketing commitments slipped
Sources: SharePoint roadmap and Statement of Work files, calendar 23-29 Apr 2026, Jira weekly digests, task digest 6 Sep 2026
Zava S2P agent platform
Security and agent enablement
AI governance (ZAVA / ZAG)
ERP cloud procurement
Marketing GTM (Thunderbolt)
ADVANCED
DELIVERED
SLIPPED
DECISION PENDING
AT RISK
Roadmap, business-unit opportunity scan and S2P process guide authored; 80% adoption target set
Three Zava Security trainings, Agent 365 walkthrough and security review office hour, 27-29 Apr
ZAG-5 compliance criteria overdue; ZAG-6 agent registration still unassigned
Three-vendor offer analysis and Statement of Work complete; award and kick-off not recorded
Marketing plan drafted; content contest lead and competitor research still open commitments
Notes: Q2 2026 delivery: S2P roadmap, opportunity scan and process guide authored (SharePoint, Sales and Marketing / AI Strategy sites); enablement sessions ran 27-29 Apr; ERP three-vendor analysis and Statement of Work complete with no award recorded; AI governance work (ZAG tickets) and the marketing content contest both slipped.

## Slide 3
External benchmarks say production agent adoption is still the exception, not the norm
Chart: 
| Enterprise apps embedding an agent | Enterprises with an agent in production | Fortune 500 with an agent in production | Agent pilots that reach production
Share of organisations (%) | 80 | 31 | 42 | 12
80% of enterprise apps shipped in Q1 2026 embed an agent, yet only 31% of enterprises - and 12% of pilots - reach production. EU AI Act high-risk duties applied from 2 Aug 2026; SAP shipped Joule procurement agents into Ariba in March 2026.
Sources: Gartner via digitalapplied.com; S&P Global / McKinsey via trixlyai.com; Forrester / Anaconda; informedclearly.com; news.sap.com (accessed 7 Sep 2026)
Notes: Competitor and regulatory context: SAP embedded Joule procurement agents across next-gen Ariba (SAP News Center, March 2026); comparisons of Coupa, Ariba, Ivalua and GEP report double-digit cycle-time reductions. EU AI Act high-risk obligations applied from 2 August 2026, with penalties up to 7% of global turnover.

## Slide 4
Every open risk traces to one person and two broken data connectors
DATA INTEGRITY
DELIVERY CAPACITY
GOVERNANCE TIMING
ServiceNow connector flagged 21 Aug (compliance) and Jira connector 12 Aug (data integrity); the Cowork approval flow is failing.
11 open items, 5 high priority, none waiting on anyone else - every one needs you to act.
ZAG-5 compliance criteria overdue and ZAG-6 agent registration unassigned as EU AI Act duties go live.
Three commitments to Adil Eli have been open since April and June 2026, and no recurring governance forum appears on the calendar after 29 April.
Escalation: connector remediation and the ZAG-5 compliance criteria each need a named owner and a committed date this week.
Sources: task digest 6 Sep 2026, Power Automate and connector alerts 12-31 Aug 2026, Teams chat with Adil Eli
Notes: Evidence: ServiceNow connector flagged 21 Aug 2026; Jira connector flagged 12 Aug 2026; Power Automate reported Cowork Plan Approval flow failures in August. Open commitments to Adil Eli: S2P status update awaited since 22 Apr, file due 19 Jun, update due 25 Jun.

## Slide 5
Four decisions need an owner and a date to unblock next quarter
1 ERP CONTRACT AWARD
2 CONNECTOR OWNERSHIP
3 S2P ADOPTION TARGET
4 MARKETING COMMITMENT
Confirm the vendor award so kick-off and the SAP/Ariba approval workflow can begin.
Name an owner and a date for ServiceNow and Jira connector remediation.
Confirm the 80% business-unit adoption goal and the funding behind it.
Confirm whether the user-generated content contest is still in scope.
None of the four is blocked by another team - each needs a decision recorded, not more analysis.
Sources: vendor offer analysis in Teams, ERP Statement of Work, S2P roadmap file, task digest 6 Sep 2026

## Slide 6
Next quarter closes the commitment backlog before scaling S2P adoption
Sequenced so credibility is restored first: overdue replies and connector health before any new adoption push.
1
2
3
4
SEPTEMBER
OCTOBER
NOVEMBER
DECEMBER
Clear five overdue commitments and reply to Adil Eli
Ship ZAG-5 criteria and assign ZAG-6 registration
Restore ServiceNow and Jira connector data flow
Open ERP kick-off and drive S2P adoption toward 80%
Ask of this review: confirm the four decisions on the previous slide so this sequence can start in September.
Proposed sequence: no dates for these items were committed in the source material