## Slide 1
QUARTER AT A GLANCE
Strategy landed. Delivery follow-through slipped.
AI agent program review · April–August 2026 · Built from calendar, Outlook, Teams and SharePoint activity, with public market benchmarks.
3
11
5
agent programs documented
(S2P, Sales, ESS)
open tasks carried
into the new quarter
of them high priority
or overdue

## Slide 2
Open-task load did not shrink: 11 items tracked on 27 Aug, 11 again on 6 Sep
27 Aug: 6 high · 3 medium · 2 low | 6 Sep: 5 high · 4 medium · 2 low — one item de-escalated, none closed.
Source: your daily task digests (Outlook), 27 Aug and 6 Sep 2026, compiled from email and Teams.
Chart: Open items by priority
| High priority | Medium priority | Low priority
27 Aug 2026 | 6 | 3 | 2
6 Sep 2026 | 5 | 4 | 2

## Slide 3
The market moved agents into production this year; our programs are still at document stage
AGENTS IN PRODUCTION
PILOT-TO-PRODUCTION GAP
PROCUREMENT BENCHMARKS
A mid-year 2026 industry report puts 54% of enterprises running AI agents in production.
Adoption reporting splits sharply: broad embedding, far narrower real deployment (~31%).
Hackett Group's 2026 procurement benchmark now indexes agentic AI adoption, ROI and risk.
Regulatory clock also shifted: the EU AI Act high-risk deadline of 2 Aug 2026 was deferred by the EU Digital Omnibus — relief, not removal.
Sources: ampcome.com mid-year 2026 enterprise agent report; paul-okhrem.com 2026 agent statistics; zycus.com Hackett Group 2026 benchmark; auroratrust.ai EU AI Act deadline update.

## Slide 4
Five open issues drive the quarter's risk — two are stakeholder commitments, three are platform integrity
Source: your daily task digests (6 Sep 2026), Teams chats and Microsoft 365 system notifications, Apr–Sep 2026.
Risk / issue | Evidence | Impact
Commitments to Adil Eli overdue | Due 25 Jun and 19 Jun; open 6 Sep | Stakeholder trust
S2P status request unanswered | Awaiting reply since 22 Apr | Sponsor visibility gap
ServiceNow connector degraded | Flagged 21 Aug | Compliance exposure
Jira connector; ZAG-5 overdue | Flagged 12 Aug | Governance evidence
Power Automate flows failing | Approval flow failed; one disabled | Workflow reliability

## Slide 5
Three decisions are needed before next quarter's plan can be committed
1 · OWNER FOR S2P AGENT
2 · FUND CONNECTOR FIX
3 · CONFIRM UGC CONTEST
Name one accountable owner and give Adil Eli a firm status date.
Approve remediation of the ServiceNow and Jira connectors this month.
Confirm whether the user-generated content contest is still in scope.
All three sit with Daichi Maruyama; none can be closed inside the programme team alone.
Source: open commitments and requests in your Outlook digests and Teams chats, Apr–Sep 2026.

## Slide 6
Next quarter: clear the backlog first, then move one agent from document to measured pilot
1
2
3
4
CLOSE OUT
CONNECTORS
GOVERNANCE
ADOPTION
Clear the five overdue commitments and reply to Adil Eli.
Restore ServiceNow and Jira flows; fix the failed approval flow.
Land ZAG-5 criteria and the S2P governance framework.
Move one agent from document stage to a measured pilot.
Sequence matters: the backlog and connector fixes gate any credible adoption claim next quarter.
Source: your roadmap and governance documents in SharePoint, plus open items in Outlook and Teams.