## Slide 1
QUARTERLY BUSINESS REVIEW · Q2 CY2026 · 1 APRIL – 30 JUNE
Design work shipped; the decisions behind it did not
Reconstructed from calendar, Outlook, Teams and SharePoint; status verified 7 September 2026
9
11
137
€140k
Meetings organised, all in April
Open items, 5 high priority
Days: oldest unanswered ask
ERP budget gap unresolved
Sources: Outlook, Teams, calendar and SharePoint. Status verified 6–7 September 2026.
Notes: Quarter under review is the last completed quarter, 1 April to 30 June 2026. Evidence was reconstructed from the Outlook calendar (nine events, all in April), Outlook mail, Teams chats and SharePoint/OneDrive documents, with open status verified against the Daily Task Digests of 4 and 6 September 2026. The 137 days is the age of Adil Eli's 22 April request for an S2P agent status update, still unanswered on 6 September. The 140,000 euro figure is the gap between the 250,000 euro ERP budget cap and ERPMax's 390,000 euro bid.

## Slide 2
DELIVERY SCORECARD
Enablement and strategy shipped; every open item is a reply or a decision I owe
Workstream | Status | Evidence
Agent enablement | Delivered | 6 sessions in April
Roadmap artefacts | Delivered | 5 documents authored
Agent strategy | Delivered | S2P and ESS guidance
Cloud ERP award | Stalled | Open since 26 Feb
Adil Eli requests | 3 overdue | 73 to 137 days
Governance tickets | In progress | ZAG-5 overdue
DELIVERED
Six enablement sessions and eight documents.
STALLED
The ERP award, undecided since 26 February.
OVERDUE
Three replies to Adil Eli, oldest 137 days.
Sources: Outlook, Teams, SharePoint libraries, and the Daily Task Digests of 4 and 6 September 2026.
Notes: Delivered items are evidenced by artefacts and calendar entries. The six April sessions are Vibe coding hours (23 Apr), Workforce Agent discussion and Office hours (24 Apr), Training - Zava Security (27, 28 and 29 Apr), Zava S2P Custom Agent, Agent 365 Walkthrough and Security Review Office Hour (27 Apr). The five roadmap documents sit in the Sales Agent and Zava S2P Agent Planner workspaces: draft initial roadmap, define milestones and deliverables, establish metrics and KPI linkage, identify opportunities across business units, and draft roadmap for AI/agentic integration. The three strategy documents are Strategic Guidance for Contoso's S2P Procurement Agent, Strategic Guidance for Contoso's ESS agent, and the Source-to-Pay Procurement Process Documentation Guide. Overdue ages are counted to 6 September 2026.

## Slide 3
Adoption is racing ahead of deployment, and ERP overruns are the norm
Chart: 
| Apps embedding agents, 2025 | Apps embedding agents, 2026F | Enterprises with agents live | ERP projects over budget
Share (%) | 5 | 40 | 31 | 55
Enterprise applications embedding task-specific AI agents: under 5% in 2025, forecast 40% by end-2026. Enterprises running agents in production: 31%. ERP projects exceeding budget: 55%.
Sources: Gartner via aiagentexplained.com and paul-okhrem.com; trixlyai.com; Panorama Consulting 2026 ERP Report via companieshistory.com and business-software.com. Accessed 7 September 2026.
Notes: Market context for the quarter, gathered by web search on 7 September 2026. Gartner's forecast is that 40 percent of enterprise applications will embed task-specific AI agents by the end of 2026, up from under 5 percent in 2025. Only 31 percent of enterprises report agents actually running in production, which is the gap this deck's delivery scorecard also shows internally. Panorama Consulting's 2026 ERP Report covers 170 organisations with projects completed or underway between January 2025 and January 2026; 55 percent of projects go over budget and 68 percent run longer than planned, with a mid-size implementation averaging 17.4 months against plan. That benchmark is the argument for treating the ERPMax 56 percent overrun as predictable rather than exceptional.

## Slide 4
RISKS AND ISSUES
Six risks are live; five rate high, and none is blocked on anyone else
ERP DECISION · HIGH
RESPONSIVENESS · HIGH
CONNECTORS · HIGH
MIGRATION · OVERDUE
GOVERNANCE · HIGH
CONCENTRATION · MEDIUM
All three bids exceed the €250k cap; ERPMax at €390k.
Three requests to Adil Eli overdue; oldest 137 days.
ServiceNow and Jira connectors failing since August.
Foundry Agent Service deadline of 26 August passed.
No AI system register; Article 50 standard undefined.
Zero items blocked on others; all eleven need me.
Sources: Daily Task Digests of 27 August, 4 and 6 September 2026; Microsoft 365 admin and Azure alerts; Compliance Readiness Brief, 7 September 2026.
Notes: ERP decision: the February analysis scored ERPMax 92 out of 100 but priced it at 390,000 euro against a 250,000 euro not-to-exceed budget, a 56 percent overrun; no approval is recorded since. Responsiveness: three separate Adil Eli items are overdue - the S2P agent status question of 22 April, the file due end of day 19 June, and the update-and-confirm due 25 June. Connectors: ServiceNow connector flagged 21 August as a compliance risk and the Jira connector flagged 12 August as a data-integrity risk. Migration: the Azure OpenAI Assistants to Foundry Agent Service transition had a 26 August deadline that has passed. Governance: the Compliance Readiness Brief rates the missing AI system inventory and the absent Article 50 transparency standard as High severity, with DLP and PII redaction documented but unevidenced. Concentration: the 6 September digest records zero items waiting on other people, so all eleven open items need action from Corey first.

## Slide 5
ASKS AND DECISIONS NEEDED
Four decisions unblock the quarter; each one needs a sign-off above me
01 AWARD THE ERP CONTRACT
Approve ERPMax, disqualify CloudFirst.
Finance, Legal, CISO, Sponsor
02 CLOSE THE €140k GAP
Cut scope, raise the cap, or re-bid.
Finance Director and Sponsor
03 NAME THE RACI OWNERS
Roles are assigned; people are not.
CIO
04 CONFIRM ERP ACTION OWNER
Briefings and notifications unassigned.
Team lead
Decision 02 — the four budget options from the February analysis
A · REDUCE SCOPE
Recommended in the analysis.
B · RAISE THE CAP
Budget increase to €390k.
C · USER DISCOUNT
Negotiate on 350 seats.
D · RE-BID
Three to four months' delay.
Sources: ERP offer analysis of 26 February 2026 (RFP-2026-001) in Teams; Daily Task Digests of 27 August and 4 September 2026; Compliance Readiness Brief, 7 September 2026.
Notes: The February offer analysis names the approvers explicitly: Corey Gray as Procurement Lead, plus Finance Director, Legal Counsel, CISO and Executive Sponsor. It scored ERPMax 92 out of 100 across technical capability weighted 40 percent, commercial terms 25 percent, risk and vendor stability 20 percent and CSR and compliance 15 percent, and recommended disqualifying CloudFirst ERP for failing mandatory real-time processing requirements. IntegraPro was rated conditional, acceptable only if supplier portal delivery is contractually guaranteed with penalties. Option A, scope reduction, was the analysis's recommendation. The RACI ask comes from the Compliance Readiness Brief, which found every governance control assigned to a role title with no individual named and no start date on the twelve-week timeline. The fourth ask comes from the 4 September digest, which flags the ERP procurement actions as possibly owned by the broader procurement team rather than Corey personally and recommends confirming with the team lead.

## Slide 6
NEXT-QUARTER PRIORITIES
Clear the backlog in four weeks; close the governance gap by week twelve
WEEKS 0–4
WEEKS 4–6
WEEKS 6–8
WEEKS 8–12
1
2
3
4
Close the ERP award.
Clear three overdue items.
Repair connectors, finish Foundry.
Register AI systems by risk tier.
Deploy and attest DLP.
Set the Article 50 standard.
Evidence PII redaction.
Attest EU data residency.
Define high-risk triggers.
Map NIST AI RMF onto controls.
Stand up a minuted review.
Publish competitor research.
Owner: Corey Gray, Procurement Lead
Owners: Governance Lead, Security Officer
Owners: AI Engineer, Platform Admin
Owner: AI Governance Lead
Sources: Compliance Readiness Brief remediation plan, 7 September 2026; Daily Task Digests of 4 and 6 September 2026; ERP offer analysis, 26 February 2026.
Notes: Week targets and owners are taken from the prioritised remediation table in the Compliance Readiness Brief of 7 September 2026, which sets four weeks for the AI system register and for DLP deployment and attestation, six weeks for PII redaction evidence and the Article 50 transparency standard, eight weeks for EU Data Boundary attestation and the high-risk decision threshold, ten weeks for mapping the NIST AI Risk Management Framework onto the internal control set, and twelve weeks for standing up a recurring minuted governance review. Every owner in that plan is a role title rather than a named individual, which is decision 03 on the previous slide. The competitor research item is the open self-commitment first made on 13 January 2026 in the Sales and Marketing Market Research channel, still unfulfilled 236 days later.