## Risk Register
Supply Chain Risk Register — How2Demos · scan window 5 Jun – 3 Sep 2026 · Score = Impact × Likelihood (1–5 each); severity thresholds on the Summary sheet
Risk ID | Risk | Supplier / Category | Impact (1-5) | Likelihood (1-5) | Score | Severity | Owner | Mitigation | Source | Source Type
R-01 | Internal visibility gap: no supplier, logistics, delay or shortage discussions found in email, Teams, calendar or meeting notes in the 90-day window, so this register relies on external benchmarks rather than confirmed exposures | All suppliers / governance | 3 | 5 | 15 | High | Bojan Buhac | Confirm procurement/logistics mailboxes and Teams channels are in scope; ask suppliers for current lead-time and allocation status; re-run the scan once sources are connected | M365 Work IQ scan (email, Teams, calendar, files), 5 Jun – 3 Sep 2026: 0 matching emails, 0 matching Teams messages, 0 calendar events, no meeting transcripts | Internal (M365)
R-02 | Dry bulk freight cost spike raising inbound raw-material landed cost (Baltic Dry Index 3,331 on 2 Sep, +5.5% day-on-day; 3,488 on 3 Sep, +18.8% month-on-month and +77.7% year-on-year) | Bulk raw materials / dry bulk carriers | 4 | 4 | 16 | High | Unassigned | Fix freight via forward/COA contracts for Q4; add BDI-linked escalator caps to supplier terms; review order timing to avoid peak Capesize rates | BalticDryIndex.com, 2 Sep 2026 — https://www.balticdryindex.com/ ; Trading Economics, 3 Sep 2026 — https://tradingeconomics.com/commodity/baltic | External (Web)
R-03 | Energy and fuel cost escalation feeding fuel surcharges and supplier price increases (Brent $94–96/bbl on 1–2 Sep, about $25–26.50 above a year ago, amid escalating US–Iran strikes) | Fuel / transport carriers / energy-intensive suppliers | 4 | 4 | 16 | High | Unassigned | Audit carrier fuel-surcharge formulas; budget against EIA Q3 forecast (~$85/bbl) vs spot; consolidate shipments to cut fuel exposure | Yahoo Finance, 1 Sep 2026 — https://finance.yahoo.com/energy/articles/current-price-oil-september-1-120000738.html ; dispatchtimes.com, 2 Sep 2026; EIA Short-Term Energy Outlook — https://www.eia.gov/outlooks/steo/index.php | External (Web)
R-04 | Middle East geopolitical disruption (US–Iran strikes) threatening shipping routes, energy supply and insurance costs | Ocean carriers / Middle East-routed lanes | 5 | 3 | 15 | High | Unassigned | Map suppliers and lanes exposed to Gulf/Red Sea routing; pre-qualify alternate routings and carriers; hold safety stock on critical SKUs | Outlook Business, 'Brent At $95 And Rising' — https://www.outlookbusiness.com/news/brent-at-95-and-rising-how-long-can-omcs-hold-fuel-prices | External (Web)
R-05 | Semiconductor and electronic component shortages spreading beyond GPUs to memory, networking, power and analog parts as AI demand absorbs capacity | Electronics / component distributors | 4 | 3 | 12 | Medium | Unassigned | Place long-lead orders early; qualify second sources for memory/power/analog parts; secure allocation agreements with distributors | GlobX, 'AI Chip Crunch 2026' — https://globx.eu/blog/supply-chain-insight/ai-infrastructure-semiconductor-supply-chain-2026 ; Randtech — https://randtech.com/semiconductor-shortages-2026-supply-chain/ | External (Web)
R-06 | Critical-minerals export controls and price shocks (China tungsten export controls reported to drive a 557% price surge; rare earths and antimony treated as strategic by governments) | Critical minerals / specialty materials | 4 | 3 | 12 | Medium | Unassigned | Identify BOM items containing tungsten, rare earths or antimony; qualify non-China sources; consider strategic inventory | informedclearly.com, '2026 Semiconductor Supply Chain Crisis' — https://informedclearly.com/en/ai/48139/semiconductor-supply-chain-crisis-geopolitics-ai-2026 ; NetNewsLedger, 3 Sep 2026 | External (Web)
R-07 | Industrial metals price volatility (copper, aluminum, steel) driven by tariffs, capex cycles and geopolitics; copper and zinc supply tightening | Metals / fabricated parts suppliers | 3 | 3 | 9 | Medium | Unassigned | Index-link metal content in supplier pricing; hedge or lock quarterly prices for high-volume parts; monitor LME weekly | J.P. Morgan Global Research, 21 Aug 2026 — https://www.jpmorgan.com/insights/global-research/commodities/aluminum-steel-copper-prices ; NetNewsLedger, 3 Sep 2026 — https://www.netnewsledger.com/2026/09/03/mining-update-copper-zinc-and-critical-minerals-tighten-as-ring-of-fire-construction-and-global-drilling-accelerates/ | External (Web)
R-08 | Elevated global supply chain pressure (NY Fed GSCPI 0.80 latest month, down from 1.19 the prior month but up from 0.02 a year ago; next release 4 Sep 2026) | Global logistics network | 3 | 3 | 9 | Medium | Unassigned | Track GSCPI monthly as an early-warning trigger; tighten lead-time buffers when index exceeds 1.0 | YCharts GSCPI — https://ycharts.com/indicators/global_supply_chain_pressure_index ; NY Fed — https://www.newyorkfed.org/research/policy/gscpi | External (Web)
R-09 | Container freight rate volatility on Transpacific and Asia–Europe lanes (Drewry WCI $4,473 per 40ft, down 1% week to 27 Aug; currently easing but historically volatile) | Container shipping lines / freight forwarders | 3 | 2 | 6 | Low | Unassigned | Use the current easing to lock Q4 contract rates; keep a spot/contract mix; monitor the weekly WCI release | Drewry World Container Index, 27 Aug 2026 — https://www.drewry.co.uk/supply-chain-advisors/supply-chain-expertise/world-container-index-assessed-by-drewry ; UFL Group freight update, Sep 2026 | External (Web)

## README
Supply Chain Risk Tracker — how to read this workbook
Prepared for | Bojan Buhac, How2Demos
Prepared on | 2026-09-03
Scan window | 5 Jun 2026 – 3 Sep 2026 (90 days)
Internal sources scanned (M365 Work IQ) | Outlook email, Teams chats and channels, Outlook calendar (meeting transcripts), SharePoint/OneDrive files — keywords: supplier, logistics, freight, shipment, delay, shortage, backorder, lead time, procurement, vendor
Internal scan result | No matching emails, Teams messages, calendar events or meeting transcripts were found in the window. The only file hits were prior versions of this tracker and Holcim/CRH annual reports (not supplier-specific). This gap is logged as risk R-01.
External sources | Web search, 3 Sep 2026 — Drewry, Baltic Exchange (via BalticDryIndex.com, Trading Economics), Yahoo Finance, EIA, NY Fed / YCharts, J.P. Morgan Global Research, ScrapMonster, GlobX, Randtech, informedclearly.com. Full URLs on the Benchmarks sheet.
Sheet map
Risk Register | One row per risk: risk, supplier/category, impact, likelihood, score, severity, owner, mitigation, source, source type. Score and severity are formulas.
Summary | Counts and shares by severity and by source type, severity thresholds (editable), average and highest score, and a chart.
Benchmarks | External commodity price and freight indicators with value, date, trend, related risk ID and source URL.
Scoring legend
Impact (1–5) | 1 = negligible cost/schedule effect · 3 = material cost increase or multi-week delay · 5 = production stoppage or loss of a critical supplier
Likelihood (1–5) | 1 = rare · 3 = possible within 12 months · 5 = already occurring / near certain
Score | Impact × Likelihood (1–25)
Severity | High when score ≥ High threshold (default 15); Medium when ≥ Medium threshold (default 8); otherwise Low. Change thresholds on the Summary sheet.
Notes and caveats
Owners | No internal owners were identified in email, Teams or meetings, so external risks are marked 'Unassigned' rather than guessed. Assign owners in column H of the Risk Register.
Impact / likelihood ratings | Analyst judgement based on the cited external indicators; adjust to your exposure once supplier-specific data is available.
Color legend | Severity column: red = High, amber = Medium, green = Low. Editable inputs on Summary (thresholds) are shown in blue.

## Summary
Supply Chain Risk Tracker — Summary
Scan window 5 Jun – 3 Sep 2026 · Primary source: M365 (email, Teams, calendar, files) · External benchmarks: web search (Drewry, Baltic Exchange, EIA, NY Fed, JPMorgan)
Severity | Count | Share | Definition
High | 4 | 44.44% | Score (Impact × Likelihood) at or above the High threshold
Medium | 4 | 44.44% | Score at or above the Medium threshold but below High
Low | 1 | 11.11% | Score below the Medium threshold
Total risks | 9 | 100%
Source type | Count | Share
Internal (M365) | 1 | 11.11%
External (Web) | 8 | 88.89%
Severity thresholds (edit to re-grade) | Min score
High ≥ | 15
Medium ≥ | 8
Average risk score | 12.2222
Highest risk score | 16
Check: severity counts = total (should be 0) | 0

## Benchmarks
External Benchmarks — commodity price and freight trend indicators (web search, retrieved 3 Sep 2026)
Indicator | Latest value | Unit | As of | Trend / change | Related risk | Source | URL
Drewry World Container Index (composite) | 4473 | USD per 40ft container | 2026-08-27 | Down 1% week-on-week; lower spot rates on Transpacific and Asia–Europe | R-09 | Drewry Supply Chain Advisors | https://www.drewry.co.uk/supply-chain-advisors/supply-chain-expertise/world-container-index-assessed-by-drewry
Baltic Dry Index (BDI) | 3331 | Index points | 2026-09-02 | Up 174 points (+5.5%) day-on-day; Capesize index up 421 to 5,642 | R-02 | BalticDryIndex.com / HandyBulk | https://www.balticdryindex.com/
Baltic Dry Index (BDI) | 3488 | Index points | 2026-09-03 | Up 4.71% day-on-day; +18.8% over the past month; +77.7% year-on-year | R-02 | Trading Economics | https://tradingeconomics.com/commodity/baltic
Brent crude oil (spot) | 94.11 | USD per barrel | 1 Sep 2026, 8am ET | Up $1.08 day-on-day; about $25 above a year ago | R-03 | Yahoo Finance | https://finance.yahoo.com/energy/articles/current-price-oil-september-1-120000738.html
Brent crude oil (spot) | 96.11 | USD per barrel | 2026-09-02 | Up about $2 since Tuesday morning; nearly $26.50 higher than a year ago; driven by US–Iran strikes | R-03 / R-04 | dispatchtimes.com; Outlook Business | https://dispatchtimes.com/oil-prices-today-2-september-2026/
Brent crude oil — EIA Q3 2026 forecast average | 85 | USD per barrel | Latest STEO | Forecast easing as inventories rebuild; most production expected to recover by early 2027 | R-03 | U.S. Energy Information Administration | https://www.eia.gov/outlooks/steo/index.php
NY Fed Global Supply Chain Pressure Index (GSCPI) | 0.8047 | Std. deviations from average | Latest monthly reading (next release 4 Sep 2026) | Down from 1.185 the prior month; up from 0.0239 a year ago | R-08 | YCharts / Federal Reserve Bank of New York | https://ycharts.com/indicators/global_supply_chain_pressure_index
Industrial metals outlook (copper, steel, aluminum) | Qualitative | — | 2026-08-21 | Prices highly responsive to tariffs, capex, geopolitics and manufacturing demand | R-07 | J.P. Morgan Global Research | https://www.jpmorgan.com/insights/global-research/commodities/aluminum-steel-copper-prices
North American scrap metal prices | Qualitative | — | 2026-09-01 | Copper, brass/bronze and stainless fell; aluminum and steel steady | R-07 | ScrapMonster | https://www.scrapmonster.com/news/daily-scrap-metal-price-report/north-american-scrap-metal-prices-slide-across-major-grades-on-the-index-2026-9-2/99921
Semiconductor / electronic component availability | Qualitative | — | 2026 | AI infrastructure draining memory, networking, power and analog parts; shortages spreading across the BOM | R-05 | GlobX; Randtech | https://globx.eu/blog/supply-chain-insight/ai-infrastructure-semiconductor-supply-chain-2026
Tungsten price (China export controls) | +557% surge (reported) | % change | 2026 | Export controls plus Middle East energy disruption cited as converging semiconductor supply threats | R-06 | informedclearly.com | https://informedclearly.com/en/ai/48139/semiconductor-supply-chain-crisis-geopolitics-ai-2026