## Risk Register
Supply-Chain Risk Register — Bojan Buhac, How2Demos ¦ Scan window 5 Jun – 3 Sep 2026 ¦ Prepared 3 Sep 2026
Internal M365 scan (Outlook mail, Teams chats, calendar, meeting transcripts, SharePoint/OneDrive files) returned NO supplier, logistics, delay or shortage discussions in the window. Risks below are therefore derived from external public benchmarks only and are UNVALIDATED against internal operations — confirm with your procurement/logistics leads before use.
Risk ID | Risk | Supplier / Lane | Impact (1-5) | Likelihood (1-5) | Severity | Owner | Mitigation | Source
R-01 | Ocean container spot rates volatile — Drewry WCI at $4,473/40ft on 27 Aug 2026, down 1% w/w on Transpacific and Asia–Europe, with a rise-then-dip pattern over the prior four weeks; budget exposure on contracted lanes | Ocean freight — Transpacific & Asia–Europe | 4 | 4 | Critical (16) | [Owner TBC] | Re-baseline freight budget monthly against WCI; hold index-linked clauses in carrier contracts; split volume across two carriers per lane | External — Drewry Trackers & Indices (drewry.co.uk), 27 Aug 2026; Navia Freight September 2026 Market Update
R-02 | Divergence between spot indices (SCFI global index ~3,4xx vs WCI $4,367–$4,526 range) signals unstable rate discovery and re-quote risk mid-quarter | Ocean freight — global lanes | 3 | 4 | High (12) | [Owner TBC] | Lock Q4 rates where spread narrows; require 30-day rate validity on all quotes; track SCFI and WCI weekly | External — Navia Freight September 2026 Freight Market Update; Tindex WCI live indicator (3 Sep 2026)
R-03 | Industrial metals (copper, steel, aluminium) input cost swings driven by geopolitical signals, industrial demand and policy shifts — direct BOM cost exposure | Metals suppliers — copper / steel / aluminium | 4 | 4 | Critical (16) | [Owner TBC] | Add price-adjustment clauses tied to a published index; extend hedging or fixed-price windows on the top-3 metal spend lines | External — J.P. Morgan Global Research, Metals Outlook: Copper, Steel and Aluminum price forecasts
R-04 | Steel price outlook for 2026–2027 remains forecast-dependent on demand and raw-material costs — risk of contracted price resets at renewal | Steel suppliers | 3 | 3 | Medium (9) | [Owner TBC] | Stagger renewal dates; benchmark quotes against published steel outlook before signing | External — SteelOnTheNet Steel Market Forecast 2026-2027
R-05 | No internal supplier / delay / shortage signal captured in the last 90 days — supplier-issue visibility gap, not an all-clear | All suppliers (visibility gap) | 4 | 3 | High (12) | [Owner TBC] | Stand up a named supply-chain channel or mailbox for escalations; request a monthly supplier status from each Tier-1; re-run this scan once data flows | Internal — Microsoft 365 scan (email, Teams, calendar, transcripts, files), 5 Jun – 3 Sep 2026: no matching items

## Summary
Summary — Counts by Severity
Severity = Impact x Likelihood. Critical 16-25 ¦ High 10-15 ¦ Medium 5-9 ¦ Low 1-4.
Severity | Count | Share of register
Critical | 2
High | 2
Medium | 1
Low | 0
Total
Source coverage
Internal (M365 Work IQ): 1 entry — a visibility-gap risk. No supplier, logistics, delay or shortage discussions were found in email, Teams, calendar or meeting transcripts for 5 Jun – 3 Sep 2026.
External (public benchmarks): 4 entries — Drewry World Container Index (27 Aug 2026, $4,473/40ft, -1% w/w), Navia Freight September 2026 Market Update, Tindex WCI, J.P. Morgan Metals Outlook, SteelOnTheNet 2026-2027 steel forecast.
Owners are unassigned ([Owner TBC]) because no internal accountable party was identified in the scanned content.