## Summary
Supply Chain Risk Tracker - Summary
Scan window 5 Jun - 3 Sep 2026 ¦ M365 Work IQ (email, Teams, meetings, files) as primary source, public web search for external benchmarks ¦ Prepared 3 Sep 2026
Risk count by severity
Severity | Count | % of Total | Score Range | Required Action
Critical | 3 | 15% | 20 to 25 | Immediate action; escalate to the executive sponsor
High | 12 | 60% | 12 to 19 | Named owner and a mitigation date this quarter
Medium | 5 | 25% | 6 to 11 | Monitor at the monthly KPI review
Low | 0 | 0% | 1 to 5 | Accept; re-assess quarterly
Total | 20 | 100%
Risk count by source
Source | Count | % of Total | Where It Came From
M365 file | 14 | 70% | Zava S2P Agent procurement documents in SharePoint
Web search | 6 | 30% | Public freight, commodity, lead-time and PMI indicators
Total | 20 | 100%
Register at a glance
Average severity score | 13.5
Highest severity score | 20
Risks at or above the Critical threshold | 3
Risks with no named owner yet | 6
Coverage note
The 90-day scan of Outlook mail, Teams chats and channels, the calendar and meeting transcripts returned no supplier, logistics, delay or shortage discussion - mail traffic in the window is Entra ID / PIM and Power Platform notifications, and no calendar events or transcripts exist for the period. Every internally sourced risk below therefore traces to a procurement document in SharePoint, not to a conversation. Full search coverage is itemised on the Method sheet.

## Risk Register
Supply Chain Risk Tracker - Risk Register
Scan window 5 Jun - 3 Sep 2026. Risk, Supplier / Entity, Owner, Mitigation and Source are taken from the cited record; Impact and Likelihood are analyst assessments on a 1-5 scale. Severity Score and Severity are calculated.
Risk ID | Risk | Supplier / Entity | Impact (1-5) | Likelihood (1-5) | Severity Score | Severity | Owner | Mitigation | Source | Source Type
R-01 | Supplier master data is split between SAP and Coupa with no single golden record for tax IDs, banking or diversity status | Supplier master (SAP S/4HANA + Coupa) | 4 | 5 | 20 | Critical | Master Data Management | Implement supplier master harmonisation; prioritised in the first 90 days to unlock end-to-end automation | Pillar3-Zava-S2P-Technology_and_Data, Sec. 1 - Key Integration Gaps (v0.1, 25 Mar 2026) | M365 file
R-02 | Supplier diversity and risk attributes are missing for roughly 25% of suppliers, so risk screening is incomplete | Supplier master (SAP Vendor) | 4 | 5 | 20 | Critical | Enterprise Data Governance Office / Procurement Data Steward | Enrich supplier attributes under the Procurement Data Steward; integrate TPRM/ESG/compliance flags into supplier records | Pillar3-Zava-S2P-Technology_and_Data, Sec. 2 - Known Data Quality Issues (v0.1, 25 Mar 2026) | M365 file
R-03 | Duplicate supplier records across systems (naming and address variations) risk mis-directed POs and duplicate payment | Supplier master (SAP + Coupa) | 3 | 4 | 12 | High | Master Data Management | De-duplicate as part of supplier master harmonisation; anomaly detection on duplicate invoices | Pillar3-Zava-S2P-Technology_and_Data, Sec. 2 - Known Data Quality Issues (v0.1, 25 Mar 2026) | M365 file
R-04 | Contract metadata is inconsistent (expiry, auto-renewal, governing law) and expiry dates are not consistently captured, limiting compliance checks | Contract repository (Icertis + SharePoint) | 4 | 4 | 16 | High | Legal Ops | Contract metadata extraction (OCR + structured fields); CLM integration for contract intake and metadata scheduled for Q4 | Pillar3-Zava-S2P-Technology_and_Data, Sec. 1 - Key Integration Gaps and Sec. 2 - Known Data Quality Issues (v0.1, 25 Mar 2026) | M365 file
R-05 | Invoice and goods-receipt status reaches the agent only via nightly batch, slowing payment-readiness guidance and risking late supplier payment | SAP AP (invoices and payments) | 3 | 4 | 12 | High | Accounts Payable | Build an AP status API for real-time invoice and goods-receipt status; prioritised in the first 90 days | Pillar3-Zava-S2P-Technology_and_Data, Sec. 1 - Key Integration Gaps and Sec. 2 - Data Readiness (v0.1, 25 Mar 2026) | M365 file
R-06 | Sourcing event award data has limited API coverage and is often moved by manual export or spreadsheet, weakening the award audit trail | Ariba sourcing events | 3 | 4 | 12 | High | Strategic Sourcing | Extend API coverage for sourcing award data; capture award rationale to the audit trail | Pillar3-Zava-S2P-Technology_and_Data, Sec. 1 - Key Integration Gaps (v0.1, 25 Mar 2026) | M365 file
R-07 | Median requisition-to-PO cycle time is 6.5 business days against a 2.0-day target, and RFQ cycles run 5-10 business days, compounding supplier lead-time exposure | Procurement Operations | 3 | 5 | 15 | High | Procurement Operations Manager | Guided buying and agent-assisted routing to reach a 2.0-day median; PR completeness check under 1 minute, first approver under 15 minutes | Pillar2-Zava-S2P-Business_Process_Mapping, Sec. 2 - SLA/Timing and Sec. 3 - Baseline vs Target (v0.1, 25 Mar 2026) | M365 file
R-08 | Only 68% of spend is compliant (preferred suppliers and contracts) against an 85%+ target, leaving maverick spend outside negotiated protection | Non-preferred / tail suppliers | 4 | 4 | 16 | High | Procurement Operations Manager | Enforce preferred supplier and catalogue rules; exceptions require documented justification | Pillar2-Zava-S2P-Business_Process_Mapping, Sec. 3 - Baseline and Sec. 2 - Business Rules (v0.1, 25 Mar 2026) | M365 file
R-09 | A supplier could be onboarded without active vendor-master status, sanctions screening or required certificates on file | New and unscreened suppliers | 5 | 2 | 10 | Medium | Procurement Operations + Information Security | Supplier eligibility gate on vendor master, sanctions/PEP screening and certificates; block or route restricted suppliers and countries to review | Pillar2-Zava-S2P-Business_Process_Mapping, Sec. 2 - Business Rules and Compliance Requirements; Pillar1-Zava-S2P-Business_AI_Strategy, Sec. 4 - Risk Management (v0.1, 25 Mar 2026) | M365 file
R-10 | Split purchases to the same supplier and category can bypass the $5K and $25K approval thresholds | Repeat-order suppliers | 3 | 3 | 9 | Medium | Procurement Operations Manager | Split-purchase detection flags same requester, category and supplier within 30 days; thresholds route to budget owner and procurement | Pillar2-Zava-S2P-Business_Process_Mapping, Sec. 2 - Business Rules (v0.1, 25 Mar 2026) | M365 file
R-11 | Supplier bank-account change fraud, duplicate invoices and unusual price variance against contract | Supplier banking / Accounts Payable | 5 | 2 | 10 | Medium | Accounts Payable + Procurement Operations | Anomaly detection on bank-account changes, duplicate invoices and price variance with automatic escalation to AP and Procurement Ops; banking details masked by default | Pillar5-Zava-S2P-Security_and_Governance, Sec. 3 - AI Safeguards, Fraud and integrity checks (v0.1, 25 Mar 2026) | M365 file
R-12 | Incorrect or biased supplier recommendation from the S2P agent influencing shortlist and award | S2P Procurement Agent | 3 | 3 | 9 | Medium | AI & Automation CoE / Responsible AI Lead | Grounding to approved sources with citation required; supplier shortlist and award recommendation need named approver sign-off; monitor for biased ranking signals | Pillar1-Zava-S2P-Business_AI_Strategy, Sec. 4 - Risk Management; Pillar5-Zava-S2P-Security_and_Governance, Sec. 2 - Tier 2 safeguards (v0.1, 25 Mar 2026) | M365 file
R-13 | Spend category miscoding routes tail spend to “Other”, hiding category- and supplier-level risk concentration | Tail-spend suppliers | 3 | 4 | 12 | High | Procurement Data Steward (CDO org) | Re-map categories to UNSPSC; improve spend visibility and forecasting at category and supplier level | Pillar3-Zava-S2P-Technology_and_Data, Sec. 2 - Known Data Quality Issues and Data Standards (v0.1, 25 Mar 2026) | M365 file
R-14 | Single-source awards may proceed without the documented justification the competitive-bidding policy requires | Single-source suppliers | 3 | 3 | 9 | Medium | Procurement Operations Manager | Competitive bidding above threshold and documented justification for single-source; exception rate tracked on the control monitoring dashboard | Pillar2-Zava-S2P-Business_Process_Mapping, Sec. 2 - Compliance Requirements; Pillar5-Zava-S2P-Security_and_Governance, Sec. 3 - Monitoring & Compliance (v0.1, 25 Mar 2026) | M365 file
R-15 | Ocean freight rate volatility: the Drewry World Container Index fell 1% to $4,473 per 40ft container in the week to 27 Aug 2026, having surged 9% earlier in the cycle | Ocean carriers (Transpacific, Asia-Europe) | 3 | 4 | 12 | High | [Assign owner - Logistics] | Benchmark contracted rates against the WCI quarterly; use index-linked freight clauses to cap the swing | Drewry World Container Index, week to 27 Aug 2026 (drewry.co.uk) | Web search
R-16 | Red Sea and Suez disruption continues to reroute vessels around the Cape of Good Hope, extending transit times and adding war-risk surcharges | Ocean carriers (Asia-Europe) | 4 | 4 | 16 | High | [Assign owner - Logistics] | Build the longer routing into required-by dates; dual-route critical inbound lanes; hold safety stock on Suez-dependent SKUs | Suaid Global, “Red Sea Shipping Crisis 2026: Rerouting”; GoFreight, “Maritime Disruption 2026” | Web search
R-17 | Electronic component lead times are tightening on DRAM shortages, HBM wafer shifts, AI demand and tariff impacts | Electronic component and semiconductor suppliers | 5 | 4 | 20 | Critical | [Assign owner - Category Manager, Electronics] | Extend the forecast horizon and place non-cancellable orders on constrained lines; qualify second sources; track lead times by component category quarterly | Sourceability, “Q2 2026 Electronics Lead Times” | Web search
R-18 | Commodity input price exposure: industrial prices are expected modestly lower over the remainder of 2026 but levels remain elevated, and the broadest commodities index fell 1.8% month-on-month in August | Metals and energy suppliers | 3 | 4 | 12 | High | [Assign owner - Category Manager, Direct Materials] | Re-benchmark contracted prices against published indices; use price-adjustment clauses tied to a named index rather than fixed quotes | S&P Global, “Commodity Price Watch: August 2026”; Westpac IQ, “Commodities Update August 2026” | Web search
R-19 | Supplier delivery times continued to slow in August 2026, with the manufacturing PMI at 54.6 and supply-chain constraints persisting | Manufacturing suppliers (broad) | 3 | 4 | 12 | High | [Assign owner - Procurement Operations] | Track the PMI supplier-delivery-times reading monthly as an early-warning indicator; add buffer to required-by dates on constrained categories | FreightWaves, “August’s manufacturing PMI dips to 54.6; supply chain constraints persist”, 1 Sep 2026 | Web search
R-20 | Tariff shifts, regional conflict and last-mile disruption are increasing cost volatility across freight, rail and supply-chain pressure indicators | Cross-border suppliers and carriers | 4 | 4 | 16 | High | [Assign owner - Procurement + Finance] | Model tariff scenarios into landed cost; review Incoterms and country-of-origin exposure on top categories | EY, “Supply chain quarterly update” (Q2 2026) | Web search

## Decisions
Related Decisions & Standing Commitments
No meeting transcripts or calendar events exist in the 5 Jun - 3 Sep 2026 window, so these decisions are drawn from the procurement documents in SharePoint rather than meeting notes. Items dated before 5 Jun 2026 are flagged.
Decision / Commitment | Date or Milestone | Owner | Related Risk IDs | Source
Approval thresholds updated and split-purchase detection rule added | 15 Apr 2026 (before scan window) | Process Excellence Lead | R-10 | Pillar2-Zava-S2P-Business_Process_Mapping, Sec. 4 - Change Log
Initial S2P agent workflow content documented and baselined | 25 Mar 2026 (before scan window) | Procurement Ops Lead | R-07, R-08 | Pillar2-Zava-S2P-Business_Process_Mapping, Sec. 4 - Change Log
First-90-days priority set: supplier master harmonisation, contract metadata extraction (OCR + structured fields), and an AP status API | First 90 days | Priya Shah, Procurement Transformation Lead | R-01, R-04, R-05 | Pillar3-Zava-S2P-Technology_and_Data, Sec. 1 - Key Integration Gaps (Mitigation)
Q3 milestone: add sourcing insights and offer comparison; launch supplier scorecards for the top 50 suppliers | Q3 2026 (inside scan window) | Procurement & AI CoE | R-02, R-06 | Pillar1-Zava-S2P-Business_AI_Strategy, Sec. 2 - Roadmap Milestones
Q4 milestone: integrate CLM for contract intake and metadata; expand to 5 categories and 2 regions | Q4 2026 | Procurement & AI CoE | R-04 | Pillar1-Zava-S2P-Business_AI_Strategy, Sec. 2 - Roadmap Milestones
Segregation of duties confirmed: the agent may draft and prepare, but humans approve supplier selection, award and payment-release readiness | Standing control | AI & Automation CoE | R-12, R-14 | Pillar5-Zava-S2P-Security_and_Governance, Sec. 1 - IT & Business Alignment
Scale-gate targets agreed: at least 20% cycle-time reduction, 10% compliance lift and 15% exception reduction before enterprise rollout | Stage gate 3 (scale approval) | Procurement CoE + Finance | R-07, R-08 | Pillar1-Zava-S2P-Business_AI_Strategy, Sec. 3 - ROI Measurement Framework
Review cadence set: monthly KPI review, quarterly process review, ad-hoc updates after policy or ERP releases | Standing cadence | Procurement Process Excellence Lead | All | Pillar2-Zava-S2P-Business_Process_Mapping, Sec. 4 - Review Cadence
Restricted suppliers and countries to be blocked or routed to review via TPRM/ESG/compliance feed integration | Standing control | Procurement Ops + Information Security | R-09 | Pillar1-Zava-S2P-Business_AI_Strategy, Sec. 4 - Risk Management (Mitigations)
Note: the source documents are all v0.1 dated 25 Mar 2026 - the current version on file. Two decisions predate the scan window and are included because they remain the governing rules for R-07, R-08 and R-10.

## Benchmarks
External Benchmarks - Commodity Price & Freight Trend Indicators
Public sources retrieved by web search on 3 Sep 2026. These ground the externally sourced risks R-15 to R-20; every reading below is quoted from the source named in the Source column.
Indicator | Latest Reading | As Of | What It Signals For This Register | Source | Link | Related Risk
Drewry World Container Index (composite) | $4,473 per 40ft container, down 1% week-on-week | Week to 27 Aug 2026 | Ocean spot rates easing on Transpacific and Asia-Europe, but off a volatile base - the same index surged 9% earlier in the cycle | Drewry Supply Chain Advisors | https://www.drewry.co.uk/supply-chain-advisors/supply-chain-expertise/world-container-index-assessed-by-drewry | R-15
ISM manufacturing PMI | 54.6, an eighth straight month of expansion | 2026-08-01 | Activity is still expanding while supplier delivery times keep slowing - a constraint signal, not a collapse | FreightWaves, 1 Sep 2026 | https://www.freightwaves.com/news/augusts-manufacturing-pmi-dips-to-54-6-supply-chain-constraints-persist | R-19
S&P Global Commodity Price Watch | Industrial prices modestly lower over the remainder of 2026; price levels remain elevated | 2026-08-01 | Input-cost relief is marginal - do not budget for a return to pre-run-up pricing | S&P Global Market Intelligence | https://www.spglobal.com/market-intelligence/en/news-insights/research/2026/08/commodity-price-watch-august-2026 | R-18
Westpac broad commodities index | Down 1.8% month-on-month; thermal coal down 10.2% as supply improved | 2026-08-01 | Energy-linked inputs are easing faster than metals | Westpac IQ | https://www.westpaciq.com.au/economics/2026/08/commodities-update-august-2026 | R-18
Electronic component lead times | Tightening on DRAM shortages, HBM wafer shifts, AI demand and tariff impacts | Q2 2026 | The single largest lead-time exposure in this register; plan longer horizons on memory and constrained analog/MCU lines | Sourceability Q2 2026 Lead Time Report | https://sourceability.com/post/q2-2026-lead-time-report-highlights | R-17
Red Sea / Suez routing status | Vessels still rerouting around the Cape of Good Hope; war-risk surcharges in force despite partial Suez recovery | 2026-08-01 | Longer and costlier Asia-Europe transit persists - build it into required-by dates | Suaid Global; GoFreight | https://suaidglobal.com/insights/red-sea-shipping-crisis-2026/ | R-16
NY Fed Global Supply Chain Pressure Index | Monthly gauge of global supply-chain conditions; next release 4 Sep 2026 | 2026-09-01 | Worth adding as a standing monthly early-warning input alongside the PMI | Federal Reserve Bank of New York | https://www.newyorkfed.org/research/policy/gscpi | R-19
EY supply chain quarterly update | Manufacturing momentum improved in Q2 2026, but freight, rail and supply-chain pressure indicators show rising strain | Q2 2026 | Tariff shifts, regional conflict and last-mile disruption are raising cost volatility | EY | https://www.ey.com/en_us/ey-center-for-executive-leadership/supply-chain-quarterly-update | R-20
Readings are point-in-time. Re-run the same set monthly - the PMI supplier-delivery reading and the NY Fed pressure index are the two cheapest early-warning inputs.

## Method
Method, Coverage & Sources
How this register was built, what was searched, and what each rating means. Scan window 5 Jun - 3 Sep 2026. Prepared 3 Sep 2026 for Bojan Buhac.
Scoring model
Severity Band | Min Score | What It Means | Required Action
Critical | 20 | Impact x Likelihood of 20 or more (max 25) | Immediate action; escalate to the executive sponsor
High | 12 | Impact x Likelihood of 12 to 19 | Named owner and a mitigation date this quarter
Medium | 6 | Impact x Likelihood of 6 to 11 | Monitor at the monthly KPI review
Low | 1 | Impact x Likelihood of 5 or less | Accept; re-assess quarterly
Scan coverage
Source Scanned | Result | Scope | Detail
Outlook mail | No hits | Inbox, 5 Jun - 3 Sep 2026; 100 most recent messages plus keyword search | No supplier, logistics, delay or shortage threads. Traffic in the window is Entra ID / PIM, Power Platform and digest notifications.
Teams chats and channels | No hits | All 9 chats and channels, messages since 5 Jun 2026 | No supply-chain discussion; recent activity is system join/leave events and a link share.
Calendar | No hits | 5 Jun - 3 Sep 2026, all events | No events returned for the window, so no meeting-derived risks.
Meeting transcripts | No hits | 5 Jun - 3 Sep 2026, all online meetings | No transcripts available, so decisions were taken from procurement documents instead.
SharePoint and OneDrive files | 4 documents | Tenant-wide keyword and semantic search on supplier, procurement, logistics and supply-chain terms | Zava S2P Agent pillar set (v0.1, 25 Mar 2026) - the sole internal source for this register.
Public web search | 8 indicators | Freight rates, commodity prices, component lead times, PMI and routing status | Captured in full on the Benchmarks sheet, each with a link.
How to read this register
1. Risk, Supplier / Entity, Owner, Mitigation and Source are taken from the cited record. Impact and Likelihood are analyst assessments on a 1-5 scale, not figures quoted from the source.
2. Severity Score is Impact x Likelihood and Severity is derived from it, so both update automatically when a rating is changed. The band thresholds live in cells B6 to B9 above - edit those and the whole register and Summary re-band.
3. An Owner shown in square brackets is unassigned. No owner is named in any available record for the externally sourced risks R-15 to R-20; assign one before the next review.
4. No email, Teams, calendar or transcript evidence exists in the scan window, so no risk here is sourced from a conversation. If supplier discussions live in a shared mailbox or a Team this account cannot see, re-run the scan with access to it.
5. The four internal source documents are all v0.1 dated 25 Mar 2026 - before the scan window, but the current version on file. Treat their baselines (68% compliant spend, 6.5-day cycle time) as the last published figures rather than live measurements.
Internal source documents
Document |  | Location | Used For
Pillar1-Zava-S2P-Business_AI_Strategy.docx |  | SharePoint > AIAC > Evidences > Zava S2P Agent | R-09, R-12; roadmap milestones and scale-gate targets
Pillar2-Zava-S2P-Business_Process_Mapping.docx |  | SharePoint > AIAC > Evidences > Zava S2P Agent | R-07, R-08, R-09, R-10, R-14; cycle-time and compliance baselines
Pillar3-Zava-S2P-Technology_and_Data.docx |  | SharePoint > AIAC > Evidences > Zava S2P Agent | R-01 to R-06, R-13; integration gaps and data quality issues
Pillar5-Zava-S2P-Security_and_Governance.docx |  | SharePoint > AIAC > Evidences > Zava S2P Agent | R-11, R-12, R-14; fraud controls and oversight tiers
External sources are listed with their links on the Benchmarks sheet.