## Actions
ID | Action | Owner | Source | Due Date | Status | Priority | Evidence / Quote
A-01 | Complete the pending update and confirm completion to Adil Eli | Corey Gray | Email — Daily Task Digest, Sep 6 2026 (recurring since Aug 10) | 2026-06-25 | Overdue | High | "Please complete the update and confirm once done by 25 June 2026."
A-02 | Finalize the file and send it to Adil Eli | Corey Gray | Teams chat with Adil Eli, Jun 19 2026 + Email digest Sep 6 2026 | 2026-06-19 | Overdue | High | "Hey Corey, Can you finalize the file and send it over by end of day today?"
A-03 | Reply to Adil Eli with the current status of the S2P agent | Corey Gray | Teams chat with Adil Eli, Apr 22 2026 + Email digest Sep 6 2026 | Not specified | Awaiting reply since 2026-04-22 | High | "Hi Corey. What is the status of S2P agent?"
A-04 | Remediate the ServiceNow Copilot connector (ServiceNowTickets2607141032) in the M365 Admin Portal | Corey Gray | Email — "Your Copilot connection ServiceNowTickets2607141032 needs immediate attention", Aug 21 2026 | Not specified (flagged 2026-08-21) | Open | High | "Please review the connection status in the Microsoft 365 Admin Portal."
A-05 | Repair the Jira Copilot connector (Jira2606051042) — re-authorize / fix permissions | Corey Gray | Email — Copilot connector alert, Aug 12 2026 | Not specified (flagged 2026-08-12) | Open | High | "Resolve this issue to ensure your data stays up to date."
A-06 | Review Adil Eli's document ("Quick task") and send written feedback | Corey Gray | Email — Daily Task Digests, Aug 2026 | End of week (exact date not stated) | Overdue | Medium | "Could you please review the document and share your feedback by end of this week?"
A-07 | Review and progress Jira work items ZAG-1 to ZAG-5; prioritise ZAG-5 (compliance criteria for agent behavior) | Corey Gray | Email — Jira digests, Aug 2026 | Not specified — ZAG-5 reported overdue | Overdue (ZAG-5) | Medium | "ZAG-5: Draft compliance criteria for agent behavior." reported as overdue
A-08 | Assign or action Jira item ZAG-6 — Set Up Agent Registration & Verification (ZAVA AI Governance) | Unassigned — surfaced to Corey Gray | Email — Jira weekly update, Sep 2 2026 | Not specified | Unassigned | Medium | "ZAG-6 Set Up Agent Registration & Verification — Assign to me / ZAVA AI Governance"
A-09 | Diagnose and fix the failed "Cowork Plan Approval" Power Automate flow | Corey Gray | Email — Power Automate failure notice, Aug 31 2026 | Not specified | Open | Medium | "The flow(s) listed failed in the past week and may need your attention."
A-10 | Review Azure Monitor action-group processes and ensure new email recipients complete OTP verification | Corey Gray (verify with IT/Azure team) | Email — Azure advisory, Aug 2026 | Not specified | Open — needs verification of ownership | Medium | "Review any processes that add email recipients to Azure Monitor action groups, and make sure new email recipients complete OTP verification when prompted."
A-11 | Compile and share competitor pricing / product-feature research with the Market Research team | Corey Gray (self-commitment) | Teams — Sales & Marketing / Market Research channel, Jan 13 2026 | Self-stated "later today" (2026-01-13) | Open | Low | "I've been looking into our main competitors' pricing strategies and product features. I'll share my findings with you all later today."
A-12 | Lead the user-generated content contest — share research findings or a draft plan | Corey Gray (requested by Daichi Maruyama) | Teams — Sales & Marketing / Marketing channel, Jan 13 2026 | Not specified | Open — confirm still active | Low | Daichi Maruyama: "Corey, can you take the lead on the user-generated content contest?"
A-13 | Approve ERPMax Solutions as preferred vendor and confirm the budget-mitigation option | Corey Gray (Procurement Lead) + Finance Director, Legal, CISO, Exec Sponsor | Teams — ERP procurement chat, Feb 26 2026 | Not specified | Awaiting decision | High | "Approval Required From: Corey Gray (Procurement Lead), Finance Director, Legal Counsel, CISO, Executive Sponsor"
A-14 | Issue formal clarification requests to ERPMax and IntegraPro (pricing & 3-yr TCO, SLA >=99.9% with penalties, GDPR/ISO 27001/SOC2 evidence, EMEA data-centre locations) | Corey Gray / Procurement Team | Teams — ERP procurement chat, Feb 26 2026 | Not specified | Open | High | "Issue formal clarification request to ERPMax and IntegraPro for: Pricing & 3-year TCO; SLA >=99.9% with penalties; GDPR, ISO 27001, SOC2 evidence; EMEA data center locations"
A-15 | Confirm disqualification of CloudFirst ERP and exclude from further evaluation | Corey Gray (Procurement Lead) | Teams — ERP procurement chat, Feb 26 2026 | Not specified | Awaiting decision | High | "Critical Finding: CloudFirst ERP fails mandatory real-time processing requirements and should be disqualified."
A-16 | Authorise contract negotiation with ERPMax to commence Week 2; then draft vendor notification letters, initialise SAP/ARIBA approval workflow and schedule kick-off | Corey Gray + Executive Sponsor | Teams — ERP procurement chat, Feb 26 2026 | Week 2 after approval | Blocked on A-13 | High | "Authorize contract negotiation to commence Week 2"
A-17 | Present the ERP vendor analysis to the Finance Director and brief Legal and Security stakeholders | Procurement Team (confirm whether Corey Gray personally owns) | Teams — ERP procurement chat; flagged "Verify" in Email digest Sep 4 2026 | Not specified | Open — ownership to be confirmed | Medium | "Present analysis to Finance Director; Brief Legal and Security stakeholders; Initiate contract negotiations."
A-18 | Open the Teams "Workflows" card of Aug 13 2026 and confirm whether action is required | Corey Gray | Teams — Workflows direct chat, Aug 13 2026 | Not specified | Needs verification | Low | "A Workflow card was posted in your chat on Aug 13, 2026. Insufficient detail was available to determine the specific task."
A-19 | Verify status of the Planner task "Communication Error Communication" | Corey Gray | Email — Microsoft Planner notification, Aug 17-18 2026 | Reported due/late Aug 2026 | Needs verification | Low | "The task 'Communication Error Communication' surfaced as due/late in Microsoft Planner."
A-20 | Confirm whether Azure OpenAI Assistants API is used anywhere in the ZAVA/agent estate and migrate to Microsoft Foundry Agent Service | Corey Gray (verify with platform owner) | Email — "Retirement notice: Transition Azure OpenAI Assistants APIs...", Aug 19 2026; validated via web search | 2026-08-26 (retirement date — now passed) | Overdue / verify | High | Microsoft Learn: "Existing applications that rely on the Assistants API will need to be migrated before August 26, 2026. After that retirement date, the Assistants API will no longer be available for use."

## RAID
ID | Type | Title | Description | Owner | Source | Target / Key Date | Impact | Status | Mitigation / Next Step
R-01 | Risk | ERP budget overrun | All three ERP vendors exceed the EUR 250,000 budget; ERPMax is at EUR 390,000 (+56%), requiring an executive decision on budget or scope. | Corey Gray + Executive Sponsor / Finance Director | Teams — ERP procurement chat, Feb 26 2026 | Not specified | High — award cannot proceed without budget resolution | Open | Pursue scope-reduction negotiation (Option A recommended) or seek budget increase to EUR 390,000.
R-02 | Risk | Contractual gaps in vendor proposals | No pricing, SLA or compliance data was retrievable for any vendor, leaving budget compliance, operational risk and legal risk unquantified. | Corey Gray / Procurement Team | Teams — ERP procurement chat, Feb 26 2026 | Before final award | High — legal and operational exposure | Open | "Final award must not proceed until commercial, SLA, and compliance gaps are closed contractually."
R-03 | Risk | IntegraPro roadmap dependency | IntegraPro's supplier-portal capability depends on a future release, creating delivery risk within the implementation window. | Procurement Team | Teams — ERP procurement chat, Feb 26 2026 | Not specified | Medium | "Acceptable only if supplier portal delivery is contractually guaranteed with penalties."
R-04 | Risk | Copilot connector outages degrade data integrity | The ServiceNow and Jira Copilot connectors are both flagged as needing immediate attention, so Copilot answers may be based on stale ticket and issue data. | Corey Gray | Email — connector alerts, Aug 12 & Aug 21 2026 | Not specified | Medium-High — compliance and data-integrity risk | Open | Repair/re-authorise both connectors in the M365 Admin Portal (see A-04, A-05).
R-05 | Risk | Chronic overdue commitments to Adil Eli | Three requests from Adil Eli (update confirmation, file delivery, S2P status) have been open since April-June 2026 and recur in every digest. | Corey Gray | Email digests Sep 4 & Sep 6 2026; Teams chat with Adil Eli | Originally 2026-06-19 / 2026-06-25 | Medium — stakeholder trust | Open | Clear A-01 to A-03, or send a status note with a revised ETA.
R-06 | Risk | Automation fragility | Power Automate flows have failed and one was disabled automatically; the Cowork Plan Approval flow is affected. | Corey Gray | Email — Power Automate alerts, Aug 30-31 2026 | Not specified | Medium — approvals may silently stall | Open | Review failed runs and re-enable the flow (see A-09).
A-01 | Assumption | ERPMax remains the preferred vendor | Scoring places ERPMax first at 92/100 on technical (40%), commercial (25%), risk (20%) and CSR/compliance (15%) weightings. | Corey Gray | Teams — ERP procurement chat, Feb 26 2026 | n/a | Underpins the whole award recommendation | To be confirmed | Re-run scoring once pricing and SLA data are received.
A-02 | Assumption | Scope stays Finance, HR and CRM for 350 EMEA users over 24 months | Requirement baseline as stated by Corey Gray: cloud SaaS, three modules, 350 users, EMEA, EUR 250,000, 24-month go-live, no legacy migration. | Corey Gray | Teams — ERP procurement chat, Feb 26 2026 | 24 months from contract signing | Changing scope invalidates pricing and scoring | Holds | Re-baseline if scope reduction (Option A) is chosen.
A-03 | Assumption | ERP procurement next steps are team-owned, not personal | Presenting to Finance, briefing Legal/Security and starting negotiations appear to be workflow-generated rather than direct personal assignments. | Corey Gray | Email digest Sep 4 2026 ("Verify" section) | n/a | Affects who is accountable for A-17 | Unverified | Confirm ownership with the team lead.
A-04 | Assumption | ZAG governance items remain in scope for Corey | ZAG-1 to ZAG-5 are assigned to Corey Gray under ZAVA AI Governance; ZAG-6 is still unassigned. | Corey Gray | Email — Jira digests, Aug-Sep 2026 | n/a | Determines governance workload | To be confirmed | Review the ZAG backlog in Jira.
I-01 | Issue | CloudFirst ERP fails mandatory requirements | CloudFirst ERP fails mandatory real-time processing and integration requirements and relies on future releases beyond the implementation window. | Procurement Team | Teams — ERP procurement chat, Feb 26 2026 | n/a | Reduces the field to two viable vendors | Open — disqualification pending confirmation | Formally confirm disqualification (see A-15).
I-02 | Issue | ServiceNow Copilot connector broken | Connection ServiceNowTickets2607141032 flagged as needing immediate attention. | Corey Gray | Email, Aug 21 2026 | Flagged 2026-08-21 | Compliance risk | Open | Investigate and repair in the M365 Admin Portal.
I-03 | Issue | Jira Copilot connector broken | Connection Jira2606051042 is failing, so Jira data is not staying up to date. | Corey Gray | Email, Aug 12 2026 | Flagged 2026-08-12 | Data-integrity risk | Open | Review authentication/permissions and re-authorise.
I-04 | Issue | Power Automate flow failures and one disabled flow | One or more flows failed in the past week and a separate alert reports a flow was disabled. | Corey Gray | Email, Aug 30-31 2026 | n/a | Approval workflow interruption | Open | Diagnose failed runs and re-enable.
I-05 | Issue | Overdue Jira item ZAG-5 | ZAG-5 (draft compliance criteria for agent behavior) is reported overdue. | Corey Gray | Email — Jira digest, Aug 2026 | Overdue | Governance deliverable slipping | Open | Prioritise ZAG-5 ahead of other ZAG items.
D-01 | Dependency | Executive budget decision blocks ERP award | Contract negotiation and vendor notification cannot start until the budget/scope decision and vendor approval are given. | Executive Sponsor / Finance Director | Teams — ERP procurement chat, Feb 26 2026 | Negotiation targeted for Week 2 after approval | Blocks A-14 to A-16 | Blocked | Escalate the approval decision (A-13).
D-02 | Dependency | Vendor clarification responses | Pricing, TCO, SLA and compliance evidence must come back from ERPMax and IntegraPro before scoring can be finalised. | ERPMax Solutions / IntegraPro Systems (external) | Teams — ERP procurement chat, Feb 26 2026 | Not specified | Blocks final award | Open | Issue clarification questionnaires (A-14).
D-03 | Dependency | Azure OpenAI Assistants API retirement — EXTERNAL, validated | Microsoft retires the Azure OpenAI Assistants API; applications must migrate to the Microsoft Foundry Agent Service. Validated externally: Microsoft Learn states "Existing applications that rely on the Assistants API will need to be migrated before August 26, 2026. After that retirement date, the Assistants API will no longer be available for use." | Corey Gray / platform owner | Email retirement notice, Aug 19 2026; validated via Microsoft Learn (learn.microsoft.com/en-us/answers/questions/5790094) | 2026-08-26 — date has passed | High if any agent still depends on the API | Overdue — verify exposure | Confirm whether any ZAVA/Copilot agent uses the API and migrate to Foundry Agent Service.
D-04 | Dependency | Manager approval for Cowork plan changes | Cowork plan requests route to a manager for approval via the Power Automate flow; a failing flow delays these. | Daichi Maruyama (approver) | Email — Cowork plan change notifications, Aug-Sep 2026 | n/a | Low-Medium | Active | Keep the approval flow healthy (A-09).
D-05 | Dependency | Adil Eli awaiting Corey's outputs | Adil Eli is blocked on the update confirmation, the finalised file and the S2P agent status. | Corey Gray | Teams chat with Adil Eli; Email digests | 2026-06-19 / 2026-06-25 | Medium | Overdue | Deliver A-01 to A-03.

## Sources
Source | Type | Date | What it provided
Daily Task Digest – Sunday, September 6, 2026 (self-sent email) | Email (M365) | 2026-09-06 | 11 open tasks with owners, evidence quotes and priorities
Daily Task Digest – Friday, September 4, 2026 (self-sent email) | Email (M365) | 2026-09-04 | 9 open tasks plus the ERP procurement 'verify ownership' flag
Teams chat – ERP procurement / vendor offer analysis | Teams chat (M365) | 2026-02-26 | ERP vendor scoring, budget overrun, disqualification, approvals and next actions
Teams chat with Adil Eli | Teams chat (M365) | 2026-04-22 / 2026-06-19 | S2P agent status request and the finalise-file request
Teams – Sales & Marketing (Market Research and Marketing channels) | Teams channel (M365) | 2026-01-13 | Competitor research commitment and user-generated content contest
Copilot connector alerts (ServiceNow, Jira) | Email (M365) | 2026-08-12 / 2026-08-21 | Connector failures
Microsoft Power Automate failure and disabled-flow alerts | Email (M365) | 2026-08-30 / 2026-08-31 | Cowork Plan Approval flow failures
Jira weekly updates | Email (M365) | 2026-08-26 / 2026-09-02 | ZAG work items including unassigned ZAG-6
Retirement notice: Azure OpenAI Assistants APIs | Email (M365) | 2026-08-19 | External retirement dependency
Microsoft Learn Q&A – Azure OpenAI Assistants API deprecation (learn.microsoft.com/en-us/answers/questions/5790094) | Web search (external validation) | Retrieved 2026-09-07 | Confirmed the 26 August 2026 retirement date
Meeting transcripts | Meetings (M365) | Searched 2026-06-01 to 2026-09-07 | No transcripts available — no actions sourced from meetings