## Overview
Consolidated Action & RAID Tracker
Open actions and RAID items compiled from Corey Gray's Microsoft 365 email, Teams chats and files
Field | Value
Report date | 2026-09-07
Prepared for | Corey Gray — Marketing, Paris
Primary sources | Outlook email, Microsoft Teams chats and Microsoft 365 files
External validation | Web search — see the External Checks sheet
Meeting transcripts | None available for 1 Aug – 7 Sep 2026, so actions come from email and Teams
Blank due dates | A blank due date means no deadline was stated in the source
Status values | Overdue, Open, Waiting, To verify
Sheet | What it contains
Actions | Every open action with owner, source, date raised, due date and status
RAID | Risks, assumptions, issues and dependencies with owners and sources
External Checks | External dependency dates validated against public sources
Metric | Count
Total open actions | 24
Actions — Overdue | 5
Actions — Open | 15
Actions — Waiting | 1
Actions — To verify | 3
RAID — Risks | 8
RAID — Assumptions | 7
RAID — Issues | 7
RAID — Dependencies | 8
Total RAID items | 30
Check — RAID types vs total (should be 0) | 0
Check — action statuses vs total (should be 0) | 0

## Actions
Actions — open items, owners, sources and due dates
ID | Action | Owner | Source | Date Raised | Due Date | Age (days) | Status
A-01 | Complete the pending update and confirm completion to Adil Eli | Corey Gray | Email — Daily Task Digest, 6 Sep 2026 |  | 2026-06-25 |  | Overdue
A-02 | Finalize the file and send it to Adil Eli | Corey Gray | Teams — Adil Eli 1:1, 19 Jun 2026 | 2026-06-19 | 2026-06-19 | 80 | Overdue
A-03 | Reply to Adil Eli with the current S2P agent status | Corey Gray | Teams — Adil Eli 1:1, 22 Apr 2026 | 2026-04-22 |  | 138 | Open
A-04 | Review Adil Eli's 'Quick task' document and send written feedback | Corey Gray | Email — Daily Task Digest, 4 Sep 2026 |  |  |  | Overdue
A-05 | Remediate Copilot connector ServiceNowTickets2607141032 | Corey Gray | Email — connector alert, 21 Aug 2026 | 2026-08-21 |  | 17 | Open
A-06 | Repair Copilot connector Jira2606051042 | Corey Gray | Email — connector alert, 12 Aug 2026 | 2026-08-12 |  | 26 | Open
A-07 | Diagnose and repair the 'Cowork Plan Approval' Power Automate flow | Corey Gray | Email — Daily Task Digest, 20 Aug 2026 | 2026-07-21 |  | 48 | Open
A-08 | ZAG-4 — identify the scope of AI governance | Corey Gray | Email — Jira digest, 20 Aug 2026 | 2026-07-21 |  | 48 | Overdue
A-09 | ZAG-5 — draft compliance criteria for agent behaviour | Corey Gray | Email — Jira digest, 20 Aug 2026 | 2026-07-21 |  | 48 | Overdue
A-10 | Triage open Jira items ZAG-1, ZAG-2 and ZAG-3 | Corey Gray | Email — Daily Task Digest, 6 Sep 2026 |  |  |  | Open
A-11 | ZAG-6 — set up agent registration and verification (currently unassigned) | Unassigned | Email — Jira weekly update, 2 Sep 2026 | 2026-09-02 |  | 5 | Open
A-12 | Finalise the Contoso S2P budget decision with the Finance Director | Corey Gray + Finance Director | Email — Daily Task Digest, 20 Aug 2026 | 2026-08-09 |  | 29 | Open
A-13 | Approve ERPMax Solutions as the preferred ERP vendor | Corey Gray (Procurement Lead) | Teams — ERP procurement chat, 26 Feb 2026 | 2026-02-26 |  | 193 | Open
A-14 | Select a budget mitigation option: scope reduction, budget increase, user discount or re-bid | Corey Gray + Finance Director | Teams — ERP procurement chat, 26 Feb 2026 | 2026-02-26 |  | 193 | Open
A-15 | Confirm the disqualification of CloudFirst ERP | Corey Gray (Procurement Lead) | Teams — ERP procurement chat, 26 Feb 2026 | 2026-02-26 |  | 193 | Open
A-16 | Issue clarification requests to ERPMax and IntegraPro: pricing and 3-year TCO, SLA, compliance evidence, EMEA data centres | Corey Gray | Teams — ERP procurement chat, 26 Feb 2026 | 2026-02-26 |  | 193 | Open
A-17 | Present the vendor analysis to the Finance Director and brief Legal and Security stakeholders | Procurement team — owner to confirm | Teams — ERP procurement chat; Email digest, 4 Sep 2026 | 2026-02-26 |  | 193 | To verify
A-18 | Review how email recipients are added to Azure Monitor action groups and enforce OTP verification | Corey Gray | Email — Azure advisory, Aug 2026 |  |  |  | Open
A-19 | Compile and share competitor pricing and feature research with the Market Research team | Corey Gray | Teams — Sales & Marketing / Market Research, 13 Jan 2026 | 2026-01-13 |  | 237 | Open
A-20 | Confirm whether the user-generated content contest is still active and share a draft plan | Corey Gray | Teams — Sales & Marketing / Marketing, 13 Jan 2026 | 2026-01-13 |  | 237 | Open
A-21 | Decide whether to reactivate or let the Atlassian subscription lapse | Corey Gray | Email — Daily Task Digest, 20 Aug 2026 | 2026-08-09 |  | 29 | Open
A-22 | Provide the outstanding details to the ZAVA Medical Service agent to unblock scheduling | Corey Gray | Teams — ZAVA Medical Service agent, 18 Jun 2026 | 2026-06-18 |  | 81 | Waiting
A-23 | Verify the status of the Planner task 'Communication Error Communication' | Corey Gray | Email — Planner notification, 17–18 Aug 2026 | 2026-08-17 |  | 21 | To verify
A-24 | Review the Teams Workflows card posted 13 Aug 2026 and confirm whether action is needed | Corey Gray | Teams — Workflows chat, 13 Aug 2026 | 2026-08-13 |  | 25 | To verify

## RAID
RAID — risks, assumptions, issues and dependencies
ID | Category | Description | Owner | Source | Severity | Key Date | Status
R-01 | Risk | All three ERP bids exceed the €250,000 not-to-exceed budget; ERPMax is €390,000 (+56%) | Corey Gray + Finance Director | Teams — ERP procurement chat, 26 Feb 2026 | High |  | Open
R-02 | Risk | Final ERP award cannot proceed until commercial, SLA and compliance gaps are closed contractually | Corey Gray | Teams — ERP procurement chat, 26 Feb 2026 | High |  | Open
R-03 | Risk | ServiceNow Copilot connector failure flagged as a compliance risk | Corey Gray | Email — Daily Task Digest, 6 Sep 2026 | High |  | Open
R-04 | Risk | Jira Copilot connector failure flagged as a data integrity risk | Corey Gray | Email — Daily Task Digest, 6 Sep 2026 | High |  | Open
R-05 | Risk | Cowork Plan Approval' flow failing since at least 21 Jul 2026, preventing creation of Approvals | Corey Gray | Email — Daily Task Digest, 20 Aug 2026 | Medium | 2026-07-21 | Open
R-06 | Risk | Four requests from Adil Eli open since April–June 2026; the oldest overdue since 25 Jun 2026 | Corey Gray | Email + Teams — Daily Task Digest, 6 Sep 2026 | Medium | 2026-06-25 | Open
R-07 | Risk | Re-bidding the ERP tender would add a 3–4 month delay and is unlikely to improve pricing | Corey Gray | Teams — ERP procurement chat, 26 Feb 2026 | Medium |  | Open
R-08 | Risk | Any workload still on the Azure OpenAI Assistants API is unsupported — the API retired 26 Aug 2026 | Corey Gray | Email — retirement notice, 19 Aug 2026 (web validated) | High | 2026-08-26 | Overdue
AS-01 | Assumption | ERP scope is cloud SaaS covering Finance, HR and CRM for 350 users across EMEA, greenfield, no migration | Corey Gray | Teams — ERP procurement chat, 26 Feb 2026 | — |  | Confirmed
AS-02 | Assumption | Budget is €250,000 not-to-exceed with go-live 24 months from contract signing | Corey Gray | Teams — ERP procurement chat, 26 Feb 2026 | — |  | Confirmed
AS-03 | Assumption | ERPMax scored 92/100 — technical 40%, commercial 25%, risk 20%, CSR and compliance 15% | Corey Gray | Teams — ERP procurement chat, 26 Feb 2026 | — |  | Confirmed
AS-04 | Assumption | Corey Gray is Procurement Lead and a required approver with Finance, Legal, the CISO and the Sponsor | Corey Gray | Teams — ERP procurement chat, 26 Feb 2026 | — |  | Confirmed
AS-05 | Assumption | ERP next-step actions may belong to the wider procurement team rather than Corey personally | Corey Gray | Email — Daily Task Digest, 4 Sep 2026 | — |  | To verify
AS-06 | Assumption | No open item is blocked on another person; all listed items need action from Corey Gray | Corey Gray | Email — Daily Task Digest, 6 Sep 2026 | — |  | Confirmed
AS-07 | Assumption | No meeting transcripts were available for the period, so actions come from email, Teams and files | Corey Gray | Microsoft 365 transcript search, Aug–Sep 2026 | — |  | Confirmed
I-01 | Issue | CloudFirst ERP fails mandatory real-time processing and integration requirements | Corey Gray | Teams — ERP procurement chat, 26 Feb 2026 | High |  | Open
I-02 | Issue | IntegraPro is acceptable only if supplier portal delivery is contractually guaranteed with penalties | Corey Gray | Teams — ERP procurement chat, 26 Feb 2026 | Medium |  | Open
I-03 | Issue | Pricing, SLA metrics and penalties, certifications, EMEA data residency and references missing from all bids | Corey Gray | Teams — ERP procurement chat, 26 Feb 2026 | High |  | Open
I-04 | Issue | Copilot connection ServiceNowTickets2607141032 has needed attention since 21 Aug 2026 | Corey Gray | Email — connector alert, 21 Aug 2026 | High | 2026-08-21 | Open
I-05 | Issue | Copilot connection Jira2606051042 has been broken since 12 Aug 2026 | Corey Gray | Email — connector alert, 12 Aug 2026 | High | 2026-08-12 | Open
I-06 | Issue | Jira items ZAG-4 and ZAG-5 are both overdue; ZAG-5 covers compliance criteria for agent behaviour | Corey Gray | Email — Daily Task Digest, 20 Aug 2026 | Medium | 2026-07-21 | Open
I-07 | Issue | The Atlassian subscription is being deactivated due to inactivity | Corey Gray | Email — Daily Task Digest, 20 Aug 2026 | Low |  | Open
D-01 | Dependency | Internal — ERP contract negotiation cannot start until the executive budget decision is made | Finance Director + Executive Sponsor | Teams — ERP procurement chat, 26 Feb 2026 | High |  | Blocked
D-02 | Dependency | External (vendor) — re-scoring and award depend on clarifications from ERPMax and IntegraPro | ERPMax / IntegraPro | Teams — ERP procurement chat, 26 Feb 2026 | High |  | Open
D-03 | Dependency | External (vendor) — Azure OpenAI Assistants API must be migrated to Microsoft Foundry Agent Service | Corey Gray | Email notice + Microsoft Learn (web validated) | High | 2026-08-26 | Date passed
D-04 | Dependency | External (vendor) — Azure Monitor action groups now require OTP verification for new email recipients | Corey Gray | Email advisory + Microsoft Learn (web validated) | Medium | 2026-07-17 | In effect
D-05 | Dependency | External (regulatory) — EU AI Act Annex III high-risk duties, deferred from 2 Aug 2026; affects ZAG scope | Corey Gray | Web validated — EU Digital Omnibus, 29 Jun 2026 | Medium | 2027-12-02 | Date revised
D-06 | Dependency | External (vendor) — Legal sign-off needs GDPR, ISO 27001, SOC 2 Type II evidence and EMEA data residency | Legal Counsel / CISO | Teams — ERP procurement chat, 26 Feb 2026 | High |  | Open
D-07 | Dependency | Internal — contract award depends on initialising the approval workflow in SAP/ARIBA | Corey Gray | Teams — ERP procurement chat, 26 Feb 2026 | Medium |  | Open
D-08 | Dependency | Internal — connector remediation needs Microsoft 365 Admin Portal access to Search connectors | Corey Gray | Email — connector alerts, Aug 2026 | High |  | Open

## External Checks
External Checks — dependency dates validated against public sources
External dependency | Date in your records | Validated date | Verdict | Source consulted
Azure OpenAI Assistants API retirement | 26 Aug 2026 — Microsoft retirement notice email, 19 Aug 2026 | 2026-08-26 | Confirmed — matches your records | Microsoft Learn Q&A, 'Will Azure OpenAI Assistants API specifically be deprecated on August 26, 2026' (learn.microsoft.com)
Azure Monitor action group OTP verification | No date given in the Azure advisory email | 2026-07-17 | Confirmed — progressive regional rollout | Microsoft Learn Q&A, 'Clarification on email OTP for action group', and the Azure Monitor action groups documentation (learn.microsoft.com)
EU AI Act — Annex III high-risk obligations | Not stated; relevant to the ZAVA AI Governance (ZAG) work | 2027-12-02 | Revised — moved from 2 Aug 2026 | EU Council final approval of the Digital Omnibus on AI, 29 Jun 2026, reported by Gibson Dunn and Cloud Security Alliance Labs
EU AI Act — Annex I embedded high-risk systems | Not stated | 2028-08-02 | Confirmed — new deadline | Digital Omnibus on AI, Regulation (EU) 2026/1744, as summarised by innobu and regulation-ai.eu
ERP vendor SLA and compliance evidence | Required before award; not supplied by any vendor |  | Not externally verifiable | No public source — this must come directly from ERPMax and IntegraPro in response to the clarification request