## Actions
Consolidated Action Tracker — open actions from email, Teams and meetings (as of 7 Sep 2026)
Action | Due Date | ID | Owner | Source | Status
Complete the required system update and confirm completion to Adil Eli | 2026-06-25 | A-01 | Corey Gray | Email — Daily Task Digest, 6 Sep 2026 (requested by Adil Eli) | Overdue
Finalize the file and send it to Adil Eli | 2026-06-19 | A-02 | Corey Gray | Teams chat — Adil Eli, 19 Jun 2026; Daily Task Digest, 6 Sep 2026 | Overdue
Reply to Adil Eli with the current status of the S2P agent | No date stated | A-03 | Corey Gray | Teams chat — Adil Eli, 22 Apr 2026; Daily Task Digest, 6 Sep 2026 | Awaiting reply
Review the document Adil Eli sent and send feedback | "End of this week" — no date stated | A-04 | Corey Gray | Email — Daily Task Digests, 20 Aug & 6 Sep 2026 | Overdue
Remediate the ServiceNow connector issue in the M365 Admin Portal | No date stated | A-05 | Corey Gray | Email — M365 system notification, flagged 21 Aug 2026 | Open
Resolve the Jira connector issue to restore data sync | No date stated | A-06 | Corey Gray | Email — M365 system notification, flagged 12 Aug 2026 | Open
Repair the 'Cowork Plan Approval' Power Automate flow blocking approvals | No date stated | A-07 | Corey Gray | Email — Power Automate alert; recurring since 21 Jul 2026 | Overdue
ZAG-4 — identify scope of governance | No date stated | A-08 | Corey Gray | Jira via Daily Task Digest, 20 Aug 2026 | Overdue
ZAG-5 — draft compliance criteria for agent behaviour | No date stated | A-09 | Corey Gray | Jira via Daily Task Digest, 20 Aug 2026 | Overdue
ZAG-1, ZAG-2, ZAG-3 — triage and update statuses | No date stated | A-10 | Corey Gray | Jira via Daily Task Digest, 20 Aug 2026 | Open
ZAG-6 — set up agent registration & verification (currently unassigned) | No date stated | A-11 | Unassigned (ZAVA AI Governance) | Email — Jira weekly update, 2 Sep 2026 | Unassigned
Finalise the executive budget decision for the Contoso S2P project | No date stated | A-12 | Corey Gray + Finance Director | Email — Daily Task Digest, 20 Aug 2026 | Open
Approve ERPMax as preferred vendor, choose a budget mitigation option and confirm CloudFirst disqualification | No date stated | A-13 | Corey Gray (Procurement Lead) + Executive Sponsor | Teams — ERP procurement analysis, 26 Feb 2026 | Open
Issue clarification request to ERPMax and IntegraPro (pricing & 3-year TCO, SLA >=99.9% with penalties, GDPR/ISO 27001/SOC2 evidence, EMEA data centre locations) | No date stated | A-14 | Corey Gray | Teams — ERP procurement analysis, 26 Feb 2026 | Open
Validate reference customers (EMEA, 300-500 users, Finance/HR/CRM) before final award | No date stated | A-15 | Corey Gray | Teams — ERP procurement analysis, 26 Feb 2026 | Open
Migrate applications off the Azure OpenAI Assistants API to Microsoft Foundry Agent Service | 2026-08-26 | A-16 | Corey Gray | Email — retirement notice; date validated on Microsoft Learn | Overdue
Compile and share competitor pricing / feature research with the Market Research team | No date stated | A-17 | Corey Gray (self-committed) | Teams — Sales & Marketing, Market Research channel | Open
Share research or a draft plan for the user-generated content contest | No date stated | A-18 | Corey Gray (asked by Daichi Maruyama) | Teams — Marketing channel, 13 Jan 2026 | Open
Review email recipients configured in Azure Monitor action groups | No date stated | A-19 | Corey Gray | Email — Azure notification, Aug 2026 | Open
Decide whether to reactivate or cancel the Atlassian subscription | No date stated | A-20 | Corey Gray | Email — Atlassian deactivation notice, Aug 2026 | Open
Provide the requested details to the ZAVA Medical Service agent to unblock scheduling | No date stated | A-21 | Corey Gray | Teams chat — ZAVA Medical Service agent, 18 Jun 2026 | Waiting on others
Verify the status of the Planner task 'Communication Error Communication' | No date stated | A-22 | Corey Gray | Email — Microsoft Planner notification, 17-18 Aug 2026 | Open

## RAID
RAID Log — Risks, Assumptions, Issues, Dependencies (as of 7 Sep 2026)
ID | Impact | Item | Owner | Source | Status / Next step | Type
R-01 | High | All three ERP vendors exceed the EUR 250,000 budget; ERPMax at EUR 390,000 (+56%), requiring an executive decision on budget resolution or scope negotiation | Corey Gray + Finance Director | Teams — ERP procurement analysis, 26 Feb 2026 | Open — choose mitigation option (scope reduction recommended) | Risk
R-02 | High | CloudFirst ERP fails mandatory real-time processing and integration requirements and relies on future releases beyond the implementation window | Corey Gray | Teams — ERP procurement analysis, 26 Feb 2026 | Open — confirm disqualification | Risk
R-03 | Medium | IntegraPro is acceptable only if supplier portal delivery is contractually guaranteed with penalties | Corey Gray | Teams — ERP procurement analysis, 26 Feb 2026 | Open — conditional vendor | Risk
R-04 | High | ServiceNow connector flagged as a compliance risk and needing immediate attention | Corey Gray | Email — M365 notification, 21 Aug 2026 | Open — see A-05 | Risk
R-05 | Medium | Jira connector flagged as a data integrity risk; data may be out of date | Corey Gray | Email — M365 notification, 12 Aug 2026 | Open — see A-06 | Risk
R-06 | Medium | Re-bidding the ERP tender would cause a 3-4 month delay and is unlikely to improve pricing | Corey Gray | Teams — ERP procurement analysis, 26 Feb 2026 | Noted — option rejected in analysis | Risk
R-07 | Medium | Multiple commitments to Adil Eli have been open since June 2026, risking stakeholder confidence | Corey Gray | Email — Daily Task Digests, Aug-Sep 2026 | Open — see A-01 to A-04 | Risk
A-01 | Baseline | ERP scope is Finance, HR and CRM (all mandatory), cloud SaaS, 350 users across EMEA, greenfield; the existing ERP will not be migrated | Corey Gray | Teams — Corey Gray, 26 Feb 2026 | Confirmed by requester | Assumption
A-02 | Baseline | Budget is EUR 250,000 not to exceed and target go-live is 24 months from contract signing | Corey Gray | Teams — Corey Gray, 26 Feb 2026 | Under pressure — see R-01 | Assumption
A-03 | Baseline | Mandatory compliance gate: GDPR, EMEA data residency, ISO 27001, SOC2 Type II and 99.9% SaaS availability SLA | Corey Gray | Teams — RFP package summary, 26 Feb 2026 | Unevidenced — see I-01 | Assumption
A-04 | Baseline | ERPMax is the preferred vendor (92/100) subject to closing commercial, SLA and compliance gaps contractually | Corey Gray | Teams — ERP procurement analysis, 26 Feb 2026 | Pending approval — see A-13 | Assumption
A-05 | Baseline | Action items surfaced in the daily digests with no explicit deadline are treated as open until confirmed closed | Corey Gray | Email — Daily Task Digests | Assumption made for this tracker | Assumption
I-01 | High | Pricing, SLA and Compliance sheets were not retrievable for any vendor, so budget compliance, operational risk and legal risk are unquantified | Corey Gray | Teams — ERP procurement analysis, 26 Feb 2026 | Open — see A-14 | Issue
I-02 | Medium | No customer references validated for the shortlisted vendors | Corey Gray | Teams — ERP procurement analysis, 26 Feb 2026 | Open — see A-15 | Issue
I-03 | High | Jira items ZAG-4 (governance scope) and ZAG-5 (agent compliance criteria) are overdue | Corey Gray | Email — Daily Task Digest, 20 Aug 2026 | Open — see A-08, A-09 | Issue
I-04 | Medium | ZAG-6 (agent registration & verification) is unassigned in the ZAVA AI Governance space | Unassigned | Email — Jira weekly update, 2 Sep 2026 | Open — assign an owner | Issue
I-05 | High | Power Automate flow failures are recurring: the 'Cowork Plan Approval' flow has blocked approval creation since 21 Jul 2026, with further failures reported in late August | Corey Gray | Email — Power Automate alerts, Jul-Aug 2026 | Open — see A-07 | Issue
D-01 | High | EXTERNAL — Azure OpenAI Assistants API retires on 26 Aug 2026; existing applications must be migrated to Microsoft Foundry Agent Service before that date, after which the API is no longer available | Corey Gray | Email retirement notice; validated on Microsoft Learn Q&A (learn.microsoft.com) | Date has passed — confirm migration status urgently | Dependency
D-02 | High | EXTERNAL — EU AI Act: from 2 August 2026 the Commission's AI Office and national authorities began enforcing the Act, including Article 50 transparency obligations for certain AI systems; relevant to the ZAG agent governance and compliance criteria work | Corey Gray | Web search validation (ismscopilot.com summary of EU AI Act timeline) | In force — align ZAG-4 / ZAG-5 criteria | Dependency
D-03 | Low | EXTERNAL — Atlassian subscription is being deactivated due to inactivity; vendor timeline drives the reactivate-or-lapse decision | Corey Gray | Email — Atlassian notification, Aug 2026 | Open — see A-20; exact cut-off date not stated | Dependency
D-04 | High | INTERNAL — Contract negotiation with ERPMax cannot start until the preferred-vendor approval and budget mitigation option are confirmed | Corey Gray + Executive Sponsor | Teams — ERP procurement analysis, 26 Feb 2026 | Blocked by A-13 | Dependency
D-05 | Medium | INTERNAL — Initialising the approval workflow in SAP/ARIBA and scheduling the ERPMax kick-off depend on the same vendor decision | Corey Gray | Teams — ERP procurement analysis, 26 Feb 2026 | Blocked by A-13 | Dependency
D-06 | Low | INTERNAL — ZAVA Medical Service scheduling is blocked pending details from Corey Gray | Corey Gray | Teams chat — 18 Jun 2026 | Waiting — see A-21 | Dependency

## README
Consolidated Action & RAID Tracker — how to use this workbook
Item | Detail
Purpose | A single view of open actions and the RAID picture, compiled for Corey Gray on 7 September 2026.
Primary sources | Outlook email (Daily Task Digests 17 Aug - 6 Sep 2026, Jira and system notifications) and Microsoft Teams chats (Adil Eli, ERP procurement, Marketing and Market Research channels).
Meeting transcripts | No meeting transcripts were available for the period searched (10 Aug - 7 Sep 2026), so no actions were drawn from meetings.
External validation | Web search was used only to confirm external dependency dates: the Azure OpenAI Assistants API retirement (26 Aug 2026) and the EU AI Act obligations applying from 2 Aug 2026. See D-01 and D-02 on the RAID sheet.
Actions sheet | Action, owner, source, due date and status. "No date stated" means the source set no deadline - it is not an assumed date.
RAID sheet | Risks (R-), Assumptions (A-), Issues (I-) and Dependencies (D-), each with owner, impact, source and next step.
Owner note | Owners are taken verbatim from the source. Where a source named no owner, the entry says so rather than assigning one.
Summary | Count
Total open actions | 22
Overdue | 7
Open | 12
Awaiting / waiting on others | 2
Unassigned | 1
Total RAID entries | 23
Check (should be 0): 0