## Actions
Consolidated Action Item Tracker — Corey Gray
As of date (edit to recalc Days Overdue): | 2026-09-07
# | Action | Owner | Source | Due Date | Status | Priority | Days Overdue | Evidence / Notes
1 | Complete the required update and confirm completion to Adil Eli | Corey Gray | Email – request from Adil Eli (tracked in Daily Task Digest, Sep 6 2026) | 2026-06-25 | Overdue | High | 74 | "Please complete the update and confirm once done by 25 June 2026." No confirmation found in sent items.
2 | Finalize the file and send it to Adil Eli | Corey Gray | Teams chat with Adil Eli, Jun 19 2026 09:36 UTC | 2026-06-19 | Overdue | High | 80 | "Hey Corey, Can you finalize the file and send it over by end of day today?" No reply found in chat.
3 | Reply to Adil Eli with current S2P agent status | Corey Gray | Teams chat with Adil Eli, Apr 22 2026 |  | Open – awaiting reply | High |  | "Hi Corey. What is the status of S2P agent?" No due date given; unanswered since Apr 22.
4 | Remediate Copilot connector ServiceNowTickets2607141032 (data source hibernated) in M365 Admin Portal | Corey Gray | Email – Microsoft 365, "Your Copilot connection ServiceNowTickets2607141032 needs immediate attention", Aug 22 2026 | 2026-09-19 | Open | High | 0 | "To prevent the deletion of indexed items, resolve the issue by September 19, 2026." Reason: Data Source Instance is hibernated.
5 | Remediate Jira connector issue to restore data sync | Corey Gray | Email – M365 system notification, Aug 12 2026 (via Daily Task Digest) |  | Open | High |  | "Resolve this issue to ensure your data stays up to date." No deadline stated.
6 | Migrate Azure OpenAI Assistants API workloads to Foundry Agent Service (subscription ME-M365CPI81743996-bobuhac-1) | Corey Gray | Email – Microsoft Azure retirement notice, Aug 18 2026 (tracking ID LZ_6-Y1Z) | 2026-08-26 | Overdue – verify completion | High | 12 | "On 26 August 2026, we'll retire the Azure OpenAI Assistants API." Deadline validated via web (Microsoft Q&A). No evidence of completion found.
7 | Review document and share feedback with Adil Eli | Corey Gray | Email – request from Adil Eli (via Daily Task Digest, Sep 4 & Sep 6 2026) |  | Overdue | Medium |  | "Could you please review the document and share your feedback by end of this week?" Exact week not stated in source.
8 | Progress Jira work items ZAG-1 to ZAG-5 (ZAVA AI Governance); ZAG-5 compliance criteria is overdue | Corey Gray | Email – Jira weekly updates, Aug 26 & Sep 2 2026; Daily Task Digest |  | Open (ZAG-5 overdue) | Medium |  | "ZAG-4: Identify scope of governance." "ZAG-5: Draft compliance criteria for agent behavior." Due dates not in email.
9 | Assign owner for ZAG-6 "Set Up Agent Registration & Verification" (currently unassigned) | Unassigned – proposed Corey Gray | Email – Jira, "Corey Gray, here is your weekly update for 2 Sept" |  | Open | Medium |  | "Assign 1 work item from spaces you've worked in — ZAG-6 Set Up Agent Registration & Verification."
10 | Close out ERP procurement actions: stakeholder briefings, budget sign-offs, vendor notifications | Corey Gray + Executive Sponsor | Teams chat – Cloud ERP vendor offer analysis (Feb 26 2026); Daily Task Digest |  | Open | Medium |  | Analysis lists "Schedule kick-off meeting with ERPMax" and "approval workflow in SAP/ARIBA" as next steps.
11 | Investigate and fix Power Automate flow failure (Cowork Plan Approval) | Corey Gray | Email – Power Automate, "1 of your flow(s) have failed" Aug 31 2026; "Alert! We've disabled one of your flows" Aug 24 2026 |  | Open | Medium |  | "The flow(s) listed failed in the past week and may need your attention."
12 | Complete Planner task "Communication Error Communication" (plan: Absolute Technology R400 Infrastructure) | Corey Gray | Email – Planner, "You have late tasks" Aug 25 2026 | 2026-08-18 | Overdue | Medium | 20 | Planner reported the task as due 8/18/2026 and "7 days late" on Aug 25.
13 | Share competitor pricing / feature research findings with Market Research team | Corey Gray | Teams – Sales & Marketing / Market Research channel (via Daily Task Digest) |  | Open – self-commitment | Low |  | "I'll share my findings with you all later today."
14 | Confirm status of, and draft plan for, user-generated content contest | Corey Gray (requested by Daichi Maruyama) | Teams – Sales & Marketing / Marketing channel, Jan 13 2026 (via Daily Task Digest) |  | Open – self-commitment | Low |  | Daichi: "Corey, can you take the lead on the user-generated content contest?"
Summary
Total open actions | 14
Overdue (past due date) | 4
High priority | 6
No due date in source | 9

## RAID
RAID Log — Risks, Assumptions, Issues, Dependencies
ID | Type | Description | Impact / Severity | Owner | Mitigation / Next Step | Key Date | Status | Source / Validation
R-01 | Risk | Copilot connector ServiceNowTickets2607141032 is failing (data source hibernated); indexed items will be deleted if not resolved by the deadline. | High – compliance / loss of indexed ServiceNow data | Corey Gray | Re-activate the ServiceNow instance and re-check connection status in the M365 Admin Portal (Action #4). | 2026-09-19 | Open | Email – Microsoft 365, Aug 22 2026: "To prevent the deletion of indexed items, resolve the issue by September 19, 2026."
R-02 | Risk | Jira connector out of sync – Copilot answers and digests may rely on stale Jira data. | Medium – data integrity | Corey Gray | Fix connector settings and confirm sync (Action #5). |  | Open | M365 system notification, Aug 12 2026 (via Daily Task Digest Sep 6): "Resolve this issue to ensure your data stays up to date."
R-03 | Risk | Multiple requests from Adil Eli (update, file, S2P status, document review) have been open since Apr–Jun 2026, risking stakeholder confidence and downstream delays. | High – stakeholder / delivery | Corey Gray | Send a single consolidated status reply to Adil Eli with new ETAs (Actions #1, #2, #3, #7). |  | Open | Teams chat with Adil Eli (Apr 22, Jun 19 2026); Daily Task Digests Aug 23 – Sep 6 2026
A-01 | Assumption | Workloads on subscription ME-M365CPI81743996-bobuhac-1 that used the Azure OpenAI Assistants API were migrated (or were not in production) before retirement. | High if false – workloads stopped working on Aug 26 | Corey Gray | Verify in Azure portal (Service Health tracking ID LZ_6-Y1Z) and confirm migration status (Action #6). | 2026-08-26 | Unverified | Email – Microsoft Azure, Aug 18 2026; no completion evidence found in mailbox or Teams
A-02 | Assumption | The user-generated content contest initiative (requested Jan 13 2026) is still active and expected by Marketing. | Low | Corey Gray / Daichi Maruyama | Confirm with Daichi Maruyama whether the contest is still planned (Action #14). |  | Unverified | Teams – Marketing channel, Jan 13 2026 (via Daily Task Digest Sep 6)
A-03 | Assumption | Items listed in the automated Daily Task Digest are still open – no completion confirmations were found in email or Teams. | Medium – tracker may include already-closed items | Corey Gray | Review each row and mark Status = Done where already completed. |  | Unverified | Daily Task Digest emails Aug 20 – Sep 6 2026
I-01 | Issue | Power Automate flow (Cowork Plan Approval) failed in the week of Aug 31; a flow was also disabled on Aug 24. | Medium – plan approvals may not process | Corey Gray | Review run history and re-enable / fix the flow (Action #11). | 2026-08-31 | Open | Email – Power Automate, "1 of your flow(s) have failed" (Aug 31) and "Alert! We've disabled one of your flows" (Aug 24)
I-02 | Issue | Planner task "Communication Error Communication" (Absolute Technology R400 Infrastructure) is late. | Medium | Corey Gray | Complete or re-plan the task in Planner (Action #12). | 2026-08-18 | Open | Email – Planner, "You have late tasks", Aug 25 2026 ("7 days late")
I-03 | Issue | Jira item ZAG-5 (Draft compliance criteria for agent behavior) is overdue; ZAG-6 has no owner. | Medium – AI governance timeline | Corey Gray | Prioritise ZAG-5 and assign ZAG-6 (Actions #8, #9). |  | Open | Email – Jira weekly updates Aug 26 & Sep 2 2026; Daily Task Digest Sep 6
D-01 | Dependency | External (vendor): Azure OpenAI Assistants API retirement – replacement is Foundry Agent Service (or Responses API for pure inference). | High | Microsoft (vendor) | Date validated on the web: Microsoft Q&A confirms retirement on August 26, 2026 (learn.microsoft.com/answers, question 5790094). | 2026-08-26 | Date passed – validated | Internal: Azure retirement email Aug 18 2026. External: Microsoft Q&A – "Existing applications that rely on the Assistants API will need to be migrated before August 26, 2026."
D-02 | Dependency | External (vendor): ServiceNow data-source instance must be un-hibernated before the M365 Copilot connector can be repaired. | High | ServiceNow instance admin | Wake the instance, then follow Microsoft's ServiceNow connector troubleshooting guidance (learn.microsoft.com, Copilot connectors). | 2026-09-19 | Open | Email – Microsoft 365, Aug 22 2026 ("Reason: Data Source Instance is hibernated"); web: Microsoft Learn ServiceNow connector troubleshooting
D-03 | Dependency | Internal: ERP procurement close-out depends on Executive Sponsor budget decision and ERPMax kick-off scheduling. | Medium | Executive Sponsor / Corey Gray | Brief stakeholders and obtain sign-off (Action #10). |  | Open | Teams chat – Cloud ERP vendor offer analysis (Feb 26 2026); Daily Task Digest Sep 6
D-04 | Dependency | Internal: Adil Eli must supply the document to review and confirm which file is expected. | Medium | Adil Eli | Ask Adil to re-share the document/file link in the status reply (R-03). |  | Open | Daily Task Digest Sep 6 2026; Teams chat with Adil Eli Jun 19 2026
Summary
Risks |  | 3
Assumptions |  | 3
Issues |  | 3
Dependencies |  | 4

## Sources & Notes
Sources & Notes
# | Source | Type | Date | Used for
1 | Daily Task Digest – Sunday, September 6, 2026 (email, self-generated) | Email – M365 Work IQ | 2026-09-06 | Actions #1–#14 consolidated list, priorities, evidence quotes
2 | Teams 1:1 chat with Adil Eli | Teams chat – M365 Work IQ | 2026-06-19 | Actions #2, #3; R-03; D-04
3 | Retirement notice: Transition Azure OpenAI Assistants APIs to Microsoft Foundry Agent Service by 26 August 2026 (Microsoft Azure) | Email – M365 Work IQ | 2026-08-18 | Action #6; A-01; D-01
4 | Your Copilot connection ServiceNowTickets2607141032 needs immediate attention (Microsoft 365) | Email – M365 Work IQ | 2026-08-22 | Action #4; R-01; D-02
5 | You have late tasks (Microsoft Planner) | Email – M365 Work IQ | 2026-08-25 | Action #12; I-02
6 | Corey Gray, here is your weekly update for 2 Sept (Jira) | Email – M365 Work IQ | 2026-09-02 | Actions #8, #9; I-03
7 | 1 of your flow(s) have failed / Alert! We've disabled one of your flows (Power Automate) | Email – M365 Work IQ | 2026-08-31 | Action #11; I-01
8 | Microsoft Q&A – "Will Azure OpenAI Assistants API specifically be deprecated on August 26th?" (learn.microsoft.com/en-us/answers/questions/5790094) | Web search – external validation | 2026-09-07 | Validated D-01 date (Aug 26, 2026)
9 | Microsoft Learn – Troubleshoot issues with the ServiceNow Knowledge connector (learn.microsoft.com/en-us/microsoft-365/copilot/connectors/servicenow-knowledge-troubleshooting) | Web search – external reference | 2026-09-07 | Remediation guidance for D-02 / R-01
Notes
• Meeting transcripts: no Teams meeting transcripts were found for Aug 10 – Sep 7, 2026, so no meeting-sourced actions are included.
• Teams: recent chats are mostly bot conversations; the only human action requests found were from Adil Eli. Channel items (Market Research, Marketing) are cited via the Daily Task Digest.
• Web search was used only to validate external dependency dates (Azure OpenAI Assistants API retirement) and connector guidance; no public benchmarks were needed for the items found.
• Change the "As of" date on the Actions sheet (cell B2) to recalculate Days Overdue. Blank Due Date = no date stated in the source.