## README
Consolidated Action-Item & RAID Tracker — Corey Gray (Marketing, Paris)
Item | Detail
Purpose | Consolidated register of open action items and a RAID log (risks, assumptions, issues, dependencies) compiled from Corey Gray's Microsoft 365 work data — Outlook email, Teams chats and channels, and meeting transcripts — with web validation of external vendor dates.
Prepared | 7 Sep 2026 — compiled by Microsoft Copilot from Microsoft 365 sources (Outlook, Teams, Planner and Jira notifications) and Bing web search.
Coverage window | Email: inbox 10 Aug – 7 Sep 2026 read in full, plus keyword searches back to Mar 2026 · Teams: all recent chats and the Sales and Marketing / AI Agent Central channels (Jan – Sep 2026) · Meeting transcripts: 1 Jan – 7 Sep 2026 searched — none found · Calendar: 27 Jul – 21 Sep 2026 — no events found.
Report as-of date (input — drives 'Days past due') | 2026-09-07
Open actions (not Done) | 20
Overdue actions | 7
Actions to verify | 5
High-priority actions | 7
Risks logged | 5
Assumptions logged | 5
Issues logged | 8
Dependencies logged | 7
Sheet: Actions | One row per open action — action, owner, source type, source, source date, due date, status, priority, evidence and link. 'Days past due' is calculated from the as-of date in B6.
Sheet: RAID | Risks, assumptions, issues and dependencies with impact, owner, source, dates, status and — for external dependencies — the web-validation result.
Sheet: Sources | Every email, Teams message and web page used, with date, link, full URL and the tracker IDs it supports.
Status legend | Open = active, no deadline passed · Overdue = stated due date has passed · Verify = likely done or stale; owner to confirm · Blocked = waiting on someone else · Done = closed. Priority: High / Medium / Low.
Method | Primary sources are the original emails and Teams messages. The auto-generated 'Daily Task Digest' emails were used only to cross-check which items are still open; each action was traced back to its original message where one exists.
Gaps | No meeting transcripts exist for Jan – Sep 2026 and the calendar has no events in the 27 Jul – 21 Sep window, so no meeting-derived actions are included. Most Teams chats are with bots (ZAVA Orders, ServiceNow); human-authored actions come from Adil Eli's chat and the Sales and Marketing channels.
External validation | Web search was used only to confirm vendor / regulatory dates: Azure OpenAI Assistants API retirement (26 Aug 2026), Azure Monitor OTP rollout (from 17 Jul 2026) and Atlassian's two-week reactivation window. See RAID D-01 – D-04 and Sources S-21 – S-24.

## Actions
Open Action Items — consolidated from Outlook email, Teams chats/channels and system notifications (status as of the README as-of date)
ID | Action | Owner | Source type | Source (subject / channel, sender) | Source date | Due date | Status | Priority | Evidence / notes | Link | Days past due
A-01 | Complete the requested update and confirm completion to Adil Eli | Corey Gray | Email | "Action required" — from Adil Eli | 2026-06-19 | 2026-06-25 | Overdue | High | Quote: "Please complete the update and confirm once done by 25 June 2026." Flagged as unresolved in every Daily Task Digest through 6 Sep 2026. | Open S-01 | 74
A-02 | Finalize the file and send it to Adil Eli | Corey Gray | Teams chat | 1:1 chat with Adil Eli (also surfaced by the email "Adil Eli mentioned you in your chat") | 2026-06-19 | 2026-06-19 | Overdue | High | Quote: "Hey Corey, Can you finalize the file and send it over by end of day today? Thanks!" No reply found in the chat. | Open S-02 | 80
A-03 | Review the document attached to "Quick task" and send feedback to Adil Eli | Corey Gray | Email | "Quick task" — from Adil Eli (with attachment) | 2026-06-19 | 2026-06-19 | Overdue | Medium | Quote: "Could you please review the document and share your feedback by end of this week?" Sent Friday 19 Jun 2026 — due date taken as the end of that working week. | Open S-03 | 80
A-04 | Reply to Adil Eli with the current status of the S2P agent | Corey Gray | Teams chat | 1:1 chat with Adil Eli | 2026-04-22 |  | Open | Medium | Quote: "Hi Corey. What is the status of S2P agent?" No reply found in the chat; still listed as awaiting reply in the 6 Sep 2026 digest. | Open S-04
A-05 | Restore Copilot connector ServiceNowTickets2607141032 (data source instance hibernated) in the Microsoft 365 admin center | Corey Gray | System notification (email) | "Your Copilot connection ServiceNowTickets2607141032 needs immediate attention" — from Microsoft 365 | 2026-08-22 | 2026-09-19 | Open | High | Quote: "To prevent the deletion of indexed items, resolve the issue by September 19, 2026." Reason given: "Data Source Instance is hibernated." | Open S-06 | 0
A-06 | Fix Copilot connector Jira2606051042 — request access from the Jira data source owner and re-authorize the connection | Corey Gray | System notification (email) | "Your Copilot connection Jira2606051042 needs immediate attention" — from Microsoft 365 | 2026-08-12 |  | Open | High | Reason given: "You don't have permission to access this data source. You can contact the owner of this data source to request permission." | Open S-07
A-07 | Investigate the failed run of Power Automate flow "Cowork Plan Approval" and confirm the flow is healthy | Corey Gray | System notification (email) | "1 of your flow(s) have failed" — from Microsoft Power Automate | 2026-08-31 |  | Verify | Medium | Failure count 1 in the week to 31 Aug 2026. "Plan request approved" notifications were generated on 7 Sep 2026, so the flow is running — review the failed run only. | Open S-08
A-08 | Fix and re-enable Power Automate flow "When agent is added or updated" (disabled after 14 days of failures) | Corey Gray | System notification (email) | "Alert! We've disabled one of your flows" — from Microsoft Power Automate | 2026-08-24 |  | Open | Medium | Quote: "Your flow has failed consistently for 14 days. We disabled it on 8/24/2026 7:28:33 PM." | Open S-09
A-09 | Complete Planner task "Communication Error Communication" (plan: Absolute Technology R400 Infrastructure) | Corey Gray | System notification (email) | "You have late tasks" — from Microsoft Planner | 2026-08-25 | 2026-08-18 | Overdue | Medium | Quote: "You have a late task Communication Error Communication … 8/18/2026 … 7 days late". Reminders were also received on 17 and 18 Aug 2026. | Open S-10 | 20
A-10 | Jira ZAG-5: Draft compliance criteria for agent behavior (ZAVA AI Governance) | Corey Gray | System notification (email) | "Corey Gray, you have work due in Jira" — from Jira | 2026-06-12 | 2026-06-08 | Overdue | Medium | Jira reminder lists ZAG-5 as due Jun 8. No later Jira reminder found — confirm current status in Jira. | Open S-11 | 91
A-11 | Jira ZAG-4: Identify scope of governance (internal vs external) (ZAVA AI Governance) | Corey Gray | System notification (email) | "Corey Gray, you have work due in Jira" — from Jira | 2026-06-12 | 2026-06-06 | Overdue | Medium | Jira reminder lists ZAG-4 as due Jun 6. Confirm current status in Jira. | Open S-11 | 93
A-12 | Decide whether to take Jira ZAG-6 "Set Up Agent Registration & Verification" (currently unassigned) | Unassigned — Jira suggests Corey Gray | System notification (email) | "Corey Gray, here is your weekly update for 2 Sept" — from Jira | 2026-09-02 |  | Open | Low | Quote: "Assign 1 work item from spaces you've worked in — ZAG-6 Set Up Agent Registration & Verification — Assign to me" (space: ZAVA AI Governance). | Open S-12
A-13 | Cloud ERP procurement (RFP-2026-001): approve ERPMax Solutions as preferred vendor, choose the budget-mitigation option, confirm CloudFirst ERP disqualification and authorize contract negotiation | Corey Gray (Procurement Lead); approvals from Finance Director, Legal Counsel, CISO, Executive Sponsor | Teams chat | Chat with the Procurement Orchestrator agent — "Comprehensive Vendor Offer Analysis – Cloud ERP Software Procurement" | 2026-02-26 |  | Open | High | Quote: "APPROVAL REQUIRED ☐ Approve ERPMax Solutions as preferred vendor ☐ Authorize Option D (Hybrid Approach) negotiation strategy ☐ Confirm disqualification of CloudFirst ERP ☐ Authorize contract negotiation to commence Week 2". No decision recorded in the chat. | S-13 (Teams chat — no direct link)
A-14 | Issue a formal clarification request to ERPMax and IntegraPro (pricing & 3-year TCO; SLA ≥ 99.9% with penalties; GDPR / ISO 27001 / SOC 2 evidence; EMEA data-centre locations) | Corey Gray (Procurement Lead) | Teams chat | Chat with the Procurement Orchestrator agent — offer analysis, "Immediate Next Actions (Decision-Ready)" | 2026-02-26 |  | Open | High | Pricing, SLA and compliance sheets were missing from all three proposals; the analysis states final award must not proceed until these gaps are closed contractually. | S-13 (Teams chat — no direct link)
A-15 | Share competitor pricing-strategy and product-feature findings with the Market Research channel | Corey Gray | Teams channel | Sales and Marketing › Market Research — post by Corey Gray | 2026-01-13 | 2026-01-13 | Verify | Low | Quote: "I've been looking into our main competitors' pricing strategies and product features. I'll share my findings with you all later today." No follow-up post found in the channel. | Open S-14 | 237
A-16 | Lead the user-generated content contest for the upcoming campaign (research best practices, draft a plan) | Corey Gray (requested by Daichi Maruyama) | Teams channel | Sales and Marketing › Marketing — post by Daichi Maruyama | 2026-01-13 |  | Verify | Low | Quote: "Corey, can you take the lead on the user-generated content contest?" Confirm whether the initiative is still active. | Open S-15
A-17 | Produce the how-to videos for the upcoming campaign | Dakota (requested by Daichi Maruyama) | Teams channel | Sales and Marketing › Marketing — post by Daichi Maruyama | 2026-01-13 |  | Verify | Low | Quote: "And Dakota, would you mind working on the how-to videos?" Same post as A-16. | Open S-15
A-18 | Confirm that Azure subscription ME-M365CPI81743996-bobuhac-1 no longer uses the Azure OpenAI Assistants API; migrate any remaining workload to Microsoft Foundry Agent Service (or the Responses API for inference-only) | Corey Gray | Vendor notice (email) | "Retirement notice: Transition Azure OpenAI Assistants APIs to Microsoft Foundry Agent Service by 26 August 2026" — from Microsoft Azure | 2026-08-18 | 2026-08-26 | Overdue | High | Quote: "On 26 August 2026, we'll retire the Azure OpenAI Assistants API … After that date, the Azure OpenAI Assistants API won't work." Retirement date confirmed on Microsoft Learn (RAID D-01). No evidence of a completed migration found. | Open S-16 | 12
A-19 | Review processes that add email recipients to Azure Monitor action groups and ensure new recipients complete OTP verification | Corey Gray | Vendor notice (email) | "Action recommended: Review new email verification requirement for Azure Monitor action groups" — from Microsoft Azure | 2026-07-18 |  | Open | Low | Rollout "starting as early as 17 July 2026"; existing addresses are unaffected. Confirmed on Microsoft Learn (RAID D-02). No deadline stated. | Open S-17
A-20 | Decide whether to reactivate the Confluence site contosolab.atlassian.net or let it lapse (data will be permanently deleted) | Corey Gray | Vendor notice (email) | "[Important Notice] Your Confluence subscription is being deactivated due to inactivity" — from Atlassian | 2026-07-23 |  | Verify | Low | Quote: "… is being deactivated due to an extended period of inactivity … any data associated with this app will be permanently deleted soon." Atlassian allows about two weeks after deactivation to request restoration (RAID D-03). | Open S-18

## RAID
RAID Log — Risks, Assumptions, Issues and Dependencies (external dependency dates validated by web search where a public source exists)
ID | Type | Description | Impact / consequence | Owner | Source | Date raised | Key date | Status | External validation (web) | Link
R-01 | Risk | Cloud ERP procurement (RFP-2026-001): all three vendor bids exceed the €250,000 not-to-exceed budget; the preferred vendor ERPMax Solutions (score 92/100) bid €390,000 (+56%). | Budget overrun or forced scope reduction; a re-bid would add a 3–4 month delay. | Corey Gray (Procurement Lead) + Finance Director | Teams chat — Procurement Orchestrator agent, "Comprehensive Vendor Offer Analysis" | 2026-02-26 |  | Open | Internal — not applicable | S-13 (Teams chat — no direct link)
R-02 | Risk | Vendor delivery risk: IntegraPro Systems is acceptable only if supplier-portal delivery is contractually guaranteed with penalties; CloudFirst ERP fails mandatory real-time processing and relies on future releases beyond the implementation window. | Delivery slippage or non-compliance with mandatory requirements if the wrong vendor is selected. | Corey Gray (Procurement Lead) | Teams chat — Procurement Orchestrator agent, offer analysis | 2026-02-26 |  | Open | Internal — not applicable | S-13 (Teams chat — no direct link)
R-03 | Risk | Evaluation data gaps: none of the three proposals provided a pricing breakdown, SLA metrics/penalties, compliance certifications (GDPR, ISO 27001, SOC 2), EMEA data-residency confirmation or customer references. | Final award cannot proceed; legal and operational risk remain unquantified until clarification responses arrive. | Corey Gray (Procurement Lead) | Teams chat — Procurement Orchestrator agent, "Data Gaps Summary" | 2026-02-26 |  | Open | Internal — not applicable | S-13 (Teams chat — no direct link)
R-04 | Risk | If Copilot connector ServiceNowTickets2607141032 is not restored by 19 Sep 2026, its indexed items will be deleted from Microsoft 365. | Loss of ServiceNow ticket data in Copilot / Microsoft Search; re-indexing effort. | Corey Gray | Email — Microsoft 365, "Your Copilot connection ServiceNowTickets2607141032 needs immediate attention" | 2026-08-22 | 2026-09-19 | Open | Date taken from the Microsoft 365 notice; web search found no public documentation of this tenant-specific retention window. | Open S-06
R-05 | Risk | Confluence site contosolab.atlassian.net was deactivated for inactivity; associated Marketplace app subscriptions are also deactivated and the data will be permanently deleted. | Permanent loss of any Confluence content and Marketplace app data. | Corey Gray | Email — Atlassian, "[Important Notice] Your Confluence subscription is being deactivated due to inactivity" | 2026-07-23 |  | Verify | Atlassian Support: after deactivation there are two weeks to contact Atlassian before data is permanently deleted — that window has most likely passed (see D-03). | Open S-18
AS-01 | Assumption | ERP scope as stated by the requester: Cloud (SaaS); Finance, HR and CRM modules; 350 users across EMEA; €250,000 total budget; go-live 24 months from contract signing; greenfield (existing ERP not migrated). | Vendor scoring and the budget analysis rest on this scope. | Corey Gray | Teams chat — Corey Gray's requirements message to the Procurement Orchestrator agent | 2026-02-26 |  | Confirmed | Internal — not applicable | S-13 (Teams chat — no direct link)
AS-02 | Assumption | Scoring weights of technical 40% / commercial 25% / risk & vendor stability 20% / CSR & compliance 15%; ERPMax ranked first (92/100) on the Requirements sheets alone because pricing, SLA and compliance sheets were not retrievable. | The ranking may change once pricing and SLA data are received. | Corey Gray (Procurement Lead) | Teams chat — Procurement Orchestrator agent, offer analysis | 2026-02-26 |  | Open | Internal — not applicable | S-13 (Teams chat — no direct link)
AS-03 | Assumption | The Microsoft retirement notice was sent because subscription ME-M365CPI81743996-bobuhac-1 uses the Azure OpenAI Assistants API; classic agents are stated as not impacted. It is assumed a real workload depends on the API — to be confirmed. | If no workload uses the API, action A-18 can be closed. | Corey Gray | Email — Microsoft Azure retirement notice (tracking ID LZ_6-Y1Z) | 2026-08-18 | 2026-08-26 | Verify | Retirement date confirmed on the web (see D-01). | Open S-16
AS-04 | Assumption | Email recipients already configured in Azure Monitor action groups keep receiving notifications; only newly added addresses need one-time passcode (OTP) verification. | Limits A-19 to process changes for new recipients. | Corey Gray | Email — Microsoft Azure, "Action recommended: Review new email verification requirement for Azure Monitor action groups" | 2026-07-18 | 2026-07-17 | Confirmed | Confirmed — Microsoft Learn "Create and manage action groups in Azure Monitor": new email addresses receive an OTP; Microsoft Q&A confirms the 17 July 2026 rollout start (see D-02). | Open S-17
AS-05 | Assumption | An item is treated as open when no reply or follow-up was found in Outlook or Teams (the same rule the auto-generated Daily Task Digest applies). A-01–A-04 and A-15–A-17 were traced to their original messages, but completion could not be confirmed. | Some "Overdue" / "Verify" items may already be done offline. | Corey Gray | Email — "📋 Daily Task Digest – Sunday, September 6, 2026" (auto-generated) | 2026-09-06 |  | Verify | Internal — not applicable | Open S-19
I-01 | Issue | Copilot connector Jira2606051042 has been failing since 12 Aug 2026 — "You don't have permission to access this data source." | Jira data in Copilot / Microsoft Search is stale or unavailable. | Corey Gray | Email — Microsoft 365, "Your Copilot connection Jira2606051042 needs immediate attention" | 2026-08-12 |  | Open | Internal — not applicable | Open S-07
I-02 | Issue | Copilot connector ServiceNowTickets2607141032 has been failing since 22 Aug 2026 — "Data Source Instance is hibernated." | ServiceNow tickets are not refreshed in Copilot; indexed items are deleted after 19 Sep 2026 (R-04). | Corey Gray | Email — Microsoft 365, "Your Copilot connection ServiceNowTickets2607141032 needs immediate attention" | 2026-08-22 | 2026-09-19 | Open | See R-04 / D-04. | Open S-06
I-03 | Issue | Power Automate flow "When agent is added or updated" failed consistently for 14 days and was turned off on 24 Aug 2026 at 7:28 PM. | Agent add/update automation is not running. | Corey Gray | Email — Microsoft Power Automate, "Alert! We've disabled one of your flows" | 2026-08-24 |  | Open | Internal — not applicable | Open S-09
I-04 | Issue | Power Automate flow "Cowork Plan Approval" recorded one failed run in the week to 31 Aug 2026 (earlier Daily Task Digests report failures since 21 Jul 2026). | Plan approval requests may intermittently fail to create approvals. "Plan request approved" notices on 7 Sep 2026 show the flow is running again. | Corey Gray | Email — Microsoft Power Automate, "1 of your flow(s) have failed" | 2026-08-31 |  | Verify | Internal — not applicable | Open S-08
I-05 | Issue | The Azure OpenAI Assistants API was retired on 26 Aug 2026; no evidence of a completed migration to Foundry Agent Service was found in email or Teams. | Any remaining Assistants API workload on the subscription stopped working after 26 Aug 2026. | Corey Gray | Email — Microsoft Azure retirement notice | 2026-08-18 | 2026-08-26 | Overdue | Retirement date confirmed on the web (see D-01). | Open S-16
I-06 | Issue | Four requests from Adil Eli have no recorded reply: S2P agent status (asked 22 Apr), finalize & send file (due 19 Jun), complete update & confirm (due 25 Jun), review document & give feedback (due end of week 19 Jun). | Stakeholder left waiting for 2–4 months; the items appear in every Daily Task Digest since July 2026. | Corey Gray | Teams chat with Adil Eli; emails "Action required" and "Quick task" from Adil Eli | 2026-06-19 | 2026-06-25 | Overdue | Internal — not applicable | Open S-01
I-07 | Issue | Planner task "Communication Error Communication" (plan: Absolute Technology R400 Infrastructure) was due 18 Aug 2026 and was 7 days late on 25 Aug. | Late deliverable in the R400 Infrastructure plan. | Corey Gray | Email — Microsoft Planner, "You have late tasks" | 2026-08-25 | 2026-08-18 | Overdue | Internal — not applicable | Open S-10
I-08 | Issue | Jira ZAG-4 (due 6 Jun 2026) and ZAG-5 (due 8 Jun 2026) in the ZAVA AI Governance space were reported overdue by Jira reminders on 8–12 Jun 2026; no later status found. | Governance scope and compliance criteria for agent behaviour remain undefined. | Corey Gray | Email — Jira, "Corey Gray, you have work due in Jira" | 2026-06-12 | 2026-06-08 | Overdue | Internal — not applicable | Open S-11
D-01 | Dependency | Vendor (Microsoft): retirement of the Azure OpenAI Assistants API on 26 Aug 2026 — replacement is Microsoft Foundry Agent Service (or the Azure OpenAI Responses API for inference-only workloads). | Drives A-18 / I-05. | Microsoft (vendor); Corey Gray for the subscription | Email — Microsoft Azure retirement notice | 2026-08-18 | 2026-08-26 | Date passed | Confirmed via web search — Microsoft Q&A / Microsoft Learn: "The Assistants API is deprecated and will be retired on August 26, 2026." | Open S-21
D-02 | Dependency | Vendor (Microsoft): Azure Monitor action groups require OTP verification for new email recipients — progressive regional rollout starting as early as 17 Jul 2026. | Drives A-19. | Microsoft (vendor); Corey Gray | Email — Microsoft Azure notice | 2026-07-18 | 2026-07-17 | In effect | Confirmed via web search — Microsoft Q&A "Clarification on email OTP for action group" quotes the same 17 July 2026 start; Microsoft Learn action-groups documentation describes the OTP step. | Open S-22
D-03 | Dependency | Vendor (Atlassian): reactivation of a deactivated Confluence site must be requested within Atlassian's restoration window before data is permanently deleted. | Determines whether A-20 is still actionable. | Atlassian (vendor); Corey Gray | Email — Atlassian deactivation notice | 2026-07-23 |  | Verify | Confirmed via web search — Atlassian Support "Reactivate a subscription": after deactivation there are two weeks to contact Atlassian before data is permanently deleted. The notice did not state the exact deletion date for contosolab.atlassian.net. | Open S-24
D-04 | Dependency | Vendor (Microsoft 365): indexed items for Copilot connector ServiceNowTickets2607141032 are retained only if the connection is fixed by 19 Sep 2026. | Drives A-05 / R-04. | Microsoft 365 (platform); Corey Gray | Email — Microsoft 365 notice | 2026-08-22 | 2026-09-19 | Open | Not independently verifiable — tenant-specific date from the Microsoft 365 notice; web search found no public documentation of this retention window. | Open S-06
D-05 | Dependency | Vendors ERPMax Solutions and IntegraPro Systems: responses to the clarification request (pricing & 3-year TCO, SLA ≥ 99.9% with penalties, GDPR / ISO 27001 / SOC 2 evidence, EMEA data-centre locations). | The final ERP award and negotiation (A-13 / A-14) cannot proceed without them. | Corey Gray (Procurement Lead) | Teams chat — Procurement Orchestrator agent, offer analysis | 2026-02-26 |  | Open | Not applicable — private vendor commitments; no public dates to validate. | S-13 (Teams chat — no direct link)
D-06 | Dependency | Internal approvals for the ERP award from the Finance Director, Legal Counsel, CISO and Executive Sponsor (preferred vendor, budget-mitigation option, CloudFirst disqualification, start of contract negotiation). | Blocks A-13. | Corey Gray (Procurement Lead) | Teams chat — Procurement Orchestrator agent, "Approval Required From" | 2026-02-26 |  | Open | Internal — not applicable | S-13 (Teams chat — no direct link)
D-07 | Dependency | The owner of the Jira data source must grant permission before Copilot connector Jira2606051042 can be re-authorized. | Blocks A-06 / I-01. | Corey Gray | Email — Microsoft 365, Jira2606051042 notice | 2026-08-12 |  | Open | Internal — not applicable | Open S-07

## Sources
Sources — every email, Teams message and web page used in this tracker (Microsoft 365 Work IQ = primary; web = external date validation only)
ID | Source type | Title / subject | From / author | Date (sent / accessed) | Link | URL | Supports (tracker IDs)
S-01 | Email | Action required | Adil Eli | 2026-06-19 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAGs3hl4AAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-01, I-06
S-02 | Teams chat | 1:1 chat message — "Can you finalize the file and send it over by end of day today?" | Adil Eli | 2026-06-19 | Open | https://teams.microsoft.com/l/message/19%3a37e063f5-2d74-4501-a798-155e8a5379dd_8cb35102-f444-4b88-bc6e-4002674b9c09%40unq.gbl.spaces/1781861814199?context=%7B%22contextType%22:%22chat%22%7D | A-02, I-06
S-03 | Email | Quick task (with attachment) | Adil Eli | 2026-06-19 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAGs3hl3AAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-03, I-06
S-04 | Teams chat | 1:1 chat message — "What is the status of S2P agent?" | Adil Eli | 2026-04-22 | Open | https://teams.microsoft.com/l/message/19%3a37e063f5-2d74-4501-a798-155e8a5379dd_8cb35102-f444-4b88-bc6e-4002674b9c09%40unq.gbl.spaces/1776845908239?context=%7B%22contextType%22:%22chat%22%7D | A-04, I-06
S-05 | Email | Adil Eli mentioned you in your chat (Teams missed-activity email) | Adil Eli (via Teams) | 2026-06-19 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAGs3hl5AAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-02
S-06 | Email (system notification) | Your Copilot connection ServiceNowTickets2607141032 needs immediate attention | Microsoft 365 | 2026-08-22 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAJOvq%2FkAAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-05, R-04, I-02, D-04
S-07 | Email (system notification) | Your Copilot connection Jira2606051042 needs immediate attention | Microsoft 365 | 2026-08-12 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAI1suIhAAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-06, I-01, D-07
S-08 | Email (system notification) | 1 of your flow(s) have failed | Microsoft Power Automate | 2026-08-31 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAJmTBSYAAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-07, I-04
S-09 | Email (system notification) | Alert! We've disabled one of your flows | Microsoft Power Automate | 2026-08-24 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAJWenKHAAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-08, I-03
S-10 | Email (system notification) | You have late tasks | Microsoft Planner (on behalf of your organization) | 2026-08-25 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAJWenKIAAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-09, I-07
S-11 | Email (system notification) | Corey Gray, you have work due in Jira | Jira | 2026-06-12 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAGeGG0oAAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-10, A-11, I-08
S-12 | Email (system notification) | Corey Gray, here is your weekly update for 2 Sept | Jira | 2026-09-02 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAJmTBSbAAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-12
S-13 | Teams chat | Chat with the Procurement Orchestrator agent — "Comprehensive Vendor Offer Analysis – Cloud ERP Software Procurement" (RFP-2026-001) | Procurement Orchestrator agent / Corey Gray | 2026-02-26 | — | No direct link available | A-13, A-14, R-01, R-02, R-03, AS-01, AS-02, D-05, D-06
S-14 | Teams channel | Sales and Marketing › Market Research — competitor research post | Corey Gray | 2026-01-13 | Open | https://teams.microsoft.com/l/message/19%3a12143dd01d644d7b8dfd955241689f5a%40thread.tacv2/1768314314320 | A-15
S-15 | Teams channel | Sales and Marketing › Marketing — campaign task assignment post | Daichi Maruyama | 2026-01-13 | Open | https://teams.microsoft.com/l/message/19%3aa6b62cf177c748d2b5459391d7e1188e%40thread.tacv2/1768314223169 | A-16, A-17
S-16 | Email (vendor notice) | Retirement notice: Transition Azure OpenAI Assistants APIs to Microsoft Foundry Agent Service by 26 August 2026 (tracking ID LZ_6-Y1Z) | Microsoft Azure | 2026-08-18 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAJIckjVAAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-18, AS-03, I-05, D-01
S-17 | Email (vendor notice) | Action recommended: Review new email verification requirement for Azure Monitor action groups | Microsoft Azure | 2026-07-18 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAHwDFSDAAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-19, AS-04, D-02
S-18 | Email (vendor notice) | [Important Notice] Your Confluence subscription is being deactivated due to inactivity | Atlassian | 2026-07-23 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAH7FsZ1AAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-20, R-05, D-03
S-19 | Email (auto-generated digest) | 📋 Daily Task Digest – Sunday, September 6, 2026 (used to cross-check open status only) | Corey Gray (AI Productivity Assistant) | 2026-09-06 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAJrU5xBAAA%3D&exvsurl=1&viewmodel=ReadMessageItem | AS-05; cross-check for A-01–A-12, A-15–A-20
S-20 | Email (system notification) | Plan request approved — evidence that the Cowork Plan Approval flow is running | Corey Gray (Power Automate flow) | 2026-09-07 | Open | https://outlook.office365.com/owa/?ItemID=AAMkADYzNTJjZDk2LWZjYTAtNDNkYi04ZDJjLWZiYjkyMzM0ZWE0NABGAAAAAAAUNtCSsQKLQI%2BnTd9py9%2B2BwC6dsD2wu9%2BTbtHZiWYBjx6AAAAAAEMAAC6dsD2wu9%2BTbtHZiWYBjx6AAJsWVFvAAA%3D&exvsurl=1&viewmodel=ReadMessageItem | A-07, I-04
S-21 | Web (Microsoft Q&A) | Will Azure OpenAI Assistants API specifically be deprecated on August 26th? | learn.microsoft.com | 2026-09-07 | Open | https://learn.microsoft.com/en-us/answers/questions/5790094/will-azure-openai-assistants-api-specifically-be-d | D-01, I-05, A-18 (date validation)
S-22 | Web (Microsoft Q&A) | Clarification on email OTP for action group | learn.microsoft.com | 2026-09-07 | Open | https://learn.microsoft.com/en-us/answers/questions/5954666/clarification-on-email-otp-for-action-group | D-02, AS-04, A-19 (date validation)
S-23 | Web (Microsoft Learn) | Create and manage action groups in Azure Monitor | learn.microsoft.com | 2026-09-07 | Open | https://learn.microsoft.com/en-us/azure/azure-monitor/alerts/action-groups | D-02, AS-04 (policy validation)
S-24 | Web (Atlassian Support) | Reactivate a subscription | support.atlassian.com | 2026-09-07 | Open | https://support.atlassian.com/subscriptions-and-billing/docs/reactivate-a-subscription/ | D-03, R-05, A-20 (policy validation)