## Overview
Action Items & RAID Tracker — Corey Gray
Purpose | Consolidated view of open actions, owners and due dates plus a RAID log, pulled from Outlook email and Teams chats. External dependency dates were checked against public Microsoft sources.
As-of date (input) | 2026-09-07
Sources searched | Outlook email (17 Aug – 7 Sep 2026 plus Daily Task Digests), Teams 1:1 chats (Adil Eli, Daichi Maruyama), meeting transcripts (none found 10 Aug – 7 Sep 2026), web validation for vendor dates
Summary | Count
Total open actions | 16
Overdue actions | 5
High-priority actions | 6
RAID items logged | 18
Risks | 5
Issues | 4
Sheet | Contents
Actions | Open action items: action, owner, source, due date, status, priority, days past due (vs. as-of date) and the evidence quote
RAID | Risks, assumptions, issues and dependencies with owner, severity, mitigation, source and key date
Source legend | Meaning
Email | Outlook message – subject and received date are named in the Source column
Teams | 1:1 chat or channel post – person/channel and date are named in the Source column
Daily Task Digest | Auto-generated daily email in your mailbox summarising open items from email and Teams; used where the original message was not directly retrievable
Web | Public Microsoft documentation used only to validate external vendor / regulatory dates (see RAID D-01, D-02)
Known gaps | No meeting transcripts were found for the period; Teams keyword search returned no channel results, so channel items come via the Daily Task Digest. Confirm digest-derived statuses with requesters.

## Actions
Open Action Items — consolidated from email, Teams and system notifications (as of 7 Sep 2026)
ID | Action | Owner | Source | Due Date | Status | Priority | Days Past Due (neg. = days left) | Evidence / Citation
A-01 | Complete the required update and confirm completion to Adil Eli | Corey Gray | Email – Adil Eli (surfaced in Daily Task Digest, 6 Sep 2026) | 2026-06-25 | Overdue | High | 74 | "Please complete the update and confirm once done by 25 June 2026."
A-02 | Finalize the file and send it to Adil Eli | Corey Gray | Teams chat with Adil Eli, 19 Jun 2026 | 2026-06-19 | Overdue | High | 80 | "Hey Corey, Can you finalize the file and send it over by end of day today? Thanks!"
A-03 | Reply to Adil Eli with the current status of the S2P agent | Corey Gray | Teams chat with Adil Eli, 22 Apr 2026 | Not set | Awaiting reply | High |  | "Hi Corey. What is the status of S2P agent?"
A-04 | Remediate the ServiceNow Copilot connector (ServiceNowTickets2607141032) in the Microsoft 365 Admin Portal | Corey Gray | Email – Microsoft 365, "Your Copilot connection ServiceNowTickets2607141032 needs immediate attention", 22 Aug 2026 | 2026-09-19 | Open – at risk | High | -12 | "To prevent the deletion of indexed items, resolve the issue by September 19, 2026." Reason: Data Source Instance is hibernated.
A-05 | Remediate the Jira Copilot connector (Jira2606051042) to restore data sync | Corey Gray | Email – Microsoft 365 notification, 12 Aug 2026 (via Daily Task Digest) | Not set | Open | High |  | "Resolve this issue to ensure your data stays up to date."
A-06 | Review the document from Adil Eli and send feedback | Corey Gray | Email – Adil Eli (via Daily Task Digest, 6 Sep 2026) | Not set ("end of this week") | Overdue | Medium |  | "Could you please review the document and share your feedback by end of this week?"
A-07 | Review Jira work items ZAG-1 to ZAG-5; prioritise ZAG-5 (draft compliance criteria for agent behaviour) | Corey Gray | Email – Jira digests, Aug 2026 (via Daily Task Digest) | Not set | Open (ZAG-5 overdue) | Medium |  | "ZAG-5: Draft compliance criteria for agent behavior." – reported as overdue
A-08 | Decide whether to take unassigned Jira item ZAG-6 "Set Up Agent Registration & Verification" (ZAVA AI Governance) | Corey Gray | Email – Jira, "Corey Gray, here is your weekly update for 2 Sept", 2 Sep 2026 | Not set | Open | Low |  | "Assign 1 work item from spaces you've worked in – ZAG-6 Set Up Agent Registration & Verification"
A-09 | Resolve the Cloud ERP procurement budget decision and close outstanding stakeholder briefings / vendor notifications | Corey Gray + Executive Sponsor | Teams chat (Contoso S2P) via Daily Task Digest, 13 Jul and 6 Sep 2026 | Not set | Pending executive decision | Medium |  | "Resolve Budget Decision — Cloud ERP Procurement … Pending Executive Decision"; "Owner: Corey Gray + Executive Sponsor"
A-10 | Investigate and fix the failing Power Automate flow "Cowork Plan Approval" | Corey Gray | Email – Microsoft Power Automate, "1 of your flow(s) have failed", 31 Aug 2026 | Not set | Open | Medium |  | "Flow name: Cowork Plan Approval – Failure count 1"
A-11 | Fix and re-enable the disabled Power Automate flow "When agent is added or updated" | Corey Gray | Email – Microsoft Power Automate, "Alert! We've disabled one of your flows", 24 Aug 2026 | Not set | Open | Medium |  | "Your flow has failed consistently for 14 days. We disabled it on 8/24/2026 7:28:33 PM."
A-12 | Complete the late Planner task "Communication Error Communication" (plan: Absolute Technology R400 Infrastructure) | Corey Gray | Email – Microsoft Planner, "You have late tasks", 25 Aug 2026 | 2026-08-18 | Overdue | Medium | 20 | "You have a late task Communication Error Communication … 8/18/2026 – 7 days late"
A-13 | Confirm Azure OpenAI Assistants API workloads were migrated to Foundry Agent Service (subscription ME-M365CPI81743996-bobuhac-1) | Corey Gray | Email – Microsoft Azure, "Retirement notice: Transition Azure OpenAI Assistants APIs to Microsoft Foundry Agent Service by 26 August 2026", 18 Aug 2026 | 2026-08-26 | Overdue – verify | High | 12 | "On 26 August 2026, we'll retire the Azure OpenAI Assistants API." Tracking ID LZ_6-Y1Z. Date validated on the web (see RAID D-01).
A-14 | Compile and share competitor pricing / feature research with the Market Research team | Corey Gray | Teams – Sales & Marketing / Market Research channel (via Daily Task Digest, 6 Sep 2026) | Not set | Open (self-commitment) | Low |  | "I'll share my findings with you all later today."
A-15 | Confirm the user-generated content contest is still active and share a draft plan with Marketing | Corey Gray (requested by Daichi Maruyama) | Teams – Sales & Marketing / Marketing channel, 13 Jan 2026 (via Daily Task Digest) | Not set | Open (needs confirmation) | Low |  | Daichi Maruyama: "Corey, can you take the lead on the user-generated content contest?"
A-16 | Verify whether the Azure Monitor action groups security advisory requires action from you | Corey Gray | Email – Microsoft Azure notification, Aug 2026 (via Daily Task Digest) | Not set | To verify | Low |  | "Review any processes that add email recipients to Azure Monitor action groups..."

## RAID
RAID Log — Risks, Assumptions, Issues and Dependencies (as of 7 Sep 2026)
ID | Type | Description | Owner | Severity | Mitigation / Next Step | Source | Status | Key Date
R-01 | Risk | Indexed ServiceNow items will be deleted if connector ServiceNowTickets2607141032 is not fixed by 19 Sep 2026 – compliance and Copilot grounding risk | Corey Gray | High | Remediate connector (A-04) before 19 Sep; data source instance is hibernated – reactivate in ServiceNow, then re-check in Admin Portal | Email – Microsoft 365, 22 Aug 2026 | Open | 2026-09-19
R-02 | Risk | Jira connector Jira2606051042 failure leaves Copilot data stale – data integrity risk | Corey Gray | High | Remediate connector (A-05) | Email – Microsoft 365 notification, 12 Aug 2026 (via Daily Task Digest) | Open | 2026-08-12
R-03 | Risk | Any workloads still on the Azure OpenAI Assistants API stopped working after the 26 Aug 2026 retirement | Corey Gray | High | Confirm migration status (A-13); inference-only workloads can use the Azure OpenAI Responses API | Email – Microsoft Azure, 18 Aug 2026; date validated via Microsoft Q&A (web) | Open – verify | 2026-08-26
R-04 | Risk | Repeated overdue commitments to Adil Eli (since Jun 2026) risk stakeholder confidence and delays on S2P / e-Bike work | Corey Gray | Medium | Clear A-01, A-02, A-03 and A-06, or send Adil Eli a status note with a new ETA | Daily Task Digest, 6 Sep 2026; Teams chat with Adil Eli | Open | 2026-06-25
R-05 | Risk | Cowork plan approvals may stall while the approval flow fails intermittently | Corey Gray | Medium | Fix flow (A-10) and monitor run history | Email – Microsoft Power Automate, 31 Aug 2026 | Open | 2026-08-31
A-01 | Assumption | Items listed in the 6 Sep 2026 Daily Task Digest remain open (digest states no items are waiting on others) | Corey Gray | Medium | Confirm each item's status with the requester before the next review | Daily Task Digest, 6 Sep 2026 | To confirm | 2026-09-06
A-02 | Assumption | Classic agents are not impacted by the Assistants API retirement and continue to work | Corey Gray | Low | No action unless workloads call the Assistants API directly | Email – Microsoft Azure, 18 Aug 2026 | Accepted | 2026-08-26
A-03 | Assumption | The user-generated content contest initiative (requested Jan 2026) is still active | Corey Gray / Daichi Maruyama | Low | Confirm with Daichi Maruyama (A-15) | Daily Task Digest, 6 Sep 2026 | To confirm | 2026-01-13
A-04 | Assumption | No meeting transcripts exist for 10 Aug – 7 Sep 2026, so no meeting-derived actions are missing from this tracker | Corey Gray | Medium | Add actions manually from any meeting notes not captured as transcripts | Transcript lookup for 10 Aug – 7 Sep 2026 returned no results | Noted | 2026-09-07
I-01 | Issue | Power Automate flow "When agent is added or updated" was disabled on 24 Aug 2026 after failing for 14 days | Corey Gray | Medium | Fix setup, test and re-enable (A-11) | Email – Microsoft Power Automate, 24 Aug 2026 | Open | 2026-08-24
I-02 | Issue | Power Automate flow "Cowork Plan Approval" failed in the week ending 31 Aug 2026 | Corey Gray | Medium | Review failure logs and fix (A-10) | Email – Microsoft Power Automate, 31 Aug 2026 | Open | 2026-08-31
I-03 | Issue | ServiceNow data source instance is hibernated – connection failure detected on ServiceNowTickets2607141032 | Corey Gray | High | Reactivate the instance and follow the Admin Portal recommended steps (A-04) | Email – Microsoft 365, 22 Aug 2026 | Open | 2026-08-22
I-04 | Issue | Planner task "Communication Error Communication" is late (due 18 Aug 2026) | Corey Gray | Medium | Complete or re-plan the task (A-12) | Email – Microsoft Planner, 25 Aug 2026 | Open | 2026-08-18
D-01 | Dependency | Microsoft retirement of the Azure OpenAI Assistants API on 26 Aug 2026 (external vendor date – validated) | Microsoft | High | Web check confirms the 26 Aug 2026 retirement: https://learn.microsoft.com/en-us/answers/questions/5790094/will-azure-openai-assistants-api-specifically-be-d | Email – Microsoft Azure, 18 Aug 2026; Microsoft Q&A (web) | Date passed | 2026-08-26
D-02 | Dependency | Microsoft 365 connector remediation deadline of 19 Sep 2026 (tenant-specific notice – no public benchmark available) | Microsoft 365 / Corey Gray | High | Date taken from the Microsoft notification; web search found only general connector troubleshooting guidance, not this deadline | Email – Microsoft 365, 22 Aug 2026 | Open | 2026-09-19
D-03 | Dependency | Cloud ERP budget decision depends on the Executive Sponsor / Finance Director | Executive Sponsor | Medium | Escalate for a decision (A-09) | Daily Task Digest, 13 Jul and 20 Aug 2026 | Pending | Not set
D-04 | Dependency | ERPMax vendor approval decisions pending confirmation from Contoso S2P AI | Corey Gray | Medium | Follow up in the Contoso S2P Teams chat | Daily Task Digest, 13 Aug 2026 | Pending | Not set
D-05 | Dependency | The document from Adil Eli must be located before review feedback can be given | Adil Eli / Corey Gray | Low | Ask Adil Eli to re-share the document (A-06) | Daily Task Digest, 6 Sep 2026 | Open | Not set