## Actions
ID | Action | Owner | Source | Due Date | Status
A-01 | Complete the required update and confirm to Adil Eli | Corey Gray | Email — Daily Task Digest, Sun 6 Sep 2026 (High Priority #1); evidence: "Please complete the update and confirm once done by 25 June 2026." | 2026-06-25 | Overdue
A-02 | Finalize the file and send it to Adil Eli | Corey Gray | Email + Teams — Daily Task Digest, Sun 6 Sep 2026 (High Priority #2); Teams chat 19 Jun 2026: "Can you finalize the file and send it over by end of day today?" | 2026-06-19 | Overdue
A-03 | Reply to Adil Eli with current status of the S2P agent | Corey Gray | Email + Teams — Daily Task Digest, Sun 6 Sep 2026 (High Priority #5); Teams 22 Apr 2026: "What is the status of S2P agent?" | Not stated (awaiting reply since 2026-04-22) | Open — awaiting your reply
A-04 | Remediate the ServiceNow connector issue in the M365 Admin Portal | Corey Gray | Email — Daily Task Digest, Sun 6 Sep 2026 (High Priority #3), flagged 21 Aug 2026; original alert "Your Copilot connection ServiceNowTickets2607141032 needs immediate attention" | Not stated (flagged 2026-08-21) | Open — compliance risk
A-05 | Resolve the Jira connector issue to restore data sync | Corey Gray | Email — Daily Task Digest, Sun 6 Sep 2026 (High Priority #4), flagged 12 Aug 2026 | Not stated (flagged 2026-08-12) | Open — data integrity risk
A-06 | Review the document from Adil Eli and send feedback | Corey Gray | Email — Daily Task Digest, Sun 6 Sep 2026 (Medium Priority #6); evidence: "review the document and share your feedback by end of this week" | Not stated ("end of week"; reported overdue) | Overdue
A-07 | Review and progress Jira work items ZAG-1 to ZAG-5; prioritise ZAG-5 (draft compliance criteria for agent behaviour) | Corey Gray | Email — Jira weekly digests 19/26 Aug and 2 Sep 2026; Daily Task Digest, Sun 6 Sep 2026 (Medium Priority #7) | Not stated (ZAG-5 reported overdue) | Open — ZAG-5 overdue
A-08 | Assign or action unassigned Jira item ZAG-6 (Set Up Agent Registration & Verification), ZAVA AI Governance | Corey Gray | Email — Jira, "Corey Gray, here is your weekly update for 2 Sept" (2 Sep 2026) | Not stated | Open — unassigned
A-09 | Work through outstanding ERP procurement actions: stakeholder briefings, budget sign-off, vendor notifications | Corey Gray (with Executive Sponsor) | Email — Daily Task Digest, Sun 6 Sep 2026 (Medium Priority #8, "Owner: Corey Gray + Executive Sponsor") | Not stated | Open
A-10 | Confirm ERPMax Solutions as preferred vendor and choose a budget mitigation option (A-D) | Corey Gray (Procurement Lead) — approvals also from Finance Director, Legal Counsel, CISO, Executive Sponsor | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 ("APPROVAL REQUIRED" section) | Not stated (contract negotiation to commence Week 2) | Open — decision pending
A-11 | Confirm disqualification of CloudFirst ERP (fails mandatory real-time processing requirements) | Corey Gray (Procurement Lead) | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 | Not stated | Open — decision pending
A-12 | Issue clarification requests to ERPMax and IntegraPro for pricing/3-year TCO, SLA >=99.9% with penalties, GDPR/ISO 27001/SOC 2 evidence, EMEA data residency | Corey Gray (Procurement Lead) | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 ("Immediate Next Actions") | Not stated (before final award) | Open
A-13 | Investigate and fix the failing Cowork Plan Approval Power Automate flow | Corey Gray | Email — "1 of your flow(s) have failed" (31 Aug 2026); "Alert! We've disabled one of your flows"; Daily Task Digest, Sun 6 Sep 2026 (#9) | Not stated | Open
A-14 | Compile and share competitor pricing/feature research with the Market Research team | Corey Gray (self-committed) | Email + Teams — Market Research channel; Daily Task Digest, Sun 6 Sep 2026 (Low Priority #10) | Not stated ("later today", referenced 24 Aug & 4 Sep 2026) | Open commitment
A-15 | Lead the user-generated content contest — share research findings or a draft plan | Corey Gray (asked by Daichi Maruyama) | Teams — Sales & Marketing / Marketing channel, 13 Jan 2026 | Not stated | Open commitment — confirm still active
A-16 | Verify whether the Azure Monitor action groups advisory needs action from you or the Azure/IT team | Corey Gray / Azure-IT team | Email — Azure notification, Aug 2026; Daily Task Digest, Sun 6 Sep 2026 (Verification section) | Not stated | To verify
A-17 | Open the Workflows Teams card dated 13 Aug 2026 and confirm whether action is required | Corey Gray | Teams — Workflows direct chat, 13 Aug 2026 (via Daily Task Digest, Sun 6 Sep 2026) | Not stated | To verify
A-18 | Verify status of Planner task "Communication Error Communication" | Corey Gray | Email — Microsoft Planner notification, 17-18 Aug 2026 | Reported due/late 2026-08-17 | To verify
A-19 | Migrate any Azure OpenAI Assistants API usage to Microsoft Foundry Agent Service | Corey Gray / owning engineering team (owner not stated in source) | Email — "Retirement notice: Transition Azure OpenAI Assistants APIs to Microsoft Foundry Agent Service by 26 August 2026" (19 Aug 2026); externally validated (see RAID D-04) | 2026-08-26 | Overdue / date passed

## RAID
ID | Type | Title | Description | Owner | Impact / Notes | Source | Status
R-01 | Risk | ERP procurement over budget | All three vendors exceed the €250,000 not-to-exceed budget; ERPMax is €390,000 (+56%), requiring an executive decision on budget or scope. | Corey Gray + Executive Sponsor | High — blocks award; mitigation options A (scope reduction, recommended), B (budget increase to €390k), C (user-based discount), D (re-scope/re-bid). | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 | Open
R-02 | Risk | ServiceNow connector compliance exposure | Copilot connection ServiceNowTickets2607141032 flagged as needing immediate attention; digest classifies it as a compliance risk. | Corey Gray | Compliance risk; unresolved since 21 Aug 2026. | Email — connector alert; Daily Task Digest, 6 Sep 2026 | Open
R-03 | Risk | Jira connector data integrity | Connector issue means data may not stay up to date; classified as a data integrity risk. | Corey Gray | Stale data feeding reporting/governance items. | Email — Daily Task Digest, 6 Sep 2026 (#4), flagged 12 Aug 2026 | Open
R-04 | Risk | Automation failures on Cowork plan approval | Power Automate reported flow failures and one flow disabled. | Corey Gray | Approval requests may silently fail. | Email — 31 Aug 2026 flow failure notice; "Alert! We've disabled one of your flows" | Open
R-05 | Risk | Long-overdue commitments to Adil Eli | Three items to Adil Eli are overdue or unanswered since Apr-Jun 2026 and keep re-surfacing. | Corey Gray | Stakeholder-confidence and delivery risk. | Email + Teams — Daily Task Digest, 6 Sep 2026 (#1, #2, #5) | Open
R-06 | Risk | Award without closed commercial/compliance gaps | Analysis states final award must not proceed until commercial, SLA and compliance gaps are closed contractually. | Corey Gray (Procurement Lead) | Legal and operational risk unquantified. | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 | Open
A-01 | Assumption | ERPMax remains the preferred vendor | ERPMax scored 92/100 across technical (40%), commercial (25%), risk & vendor stability (20%) and CSR/compliance (15%). | Corey Gray | Assumes scoring holds once pricing and SLA data are received; analysis offers to re-run scoring. | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 | Assumed
A-02 | Assumption | Scope stays Finance, HR and CRM for 350 users, EMEA, greenfield, 24-month timeline | Baseline scope stated in RFP-2026-001. | Corey Gray | Change of scope invalidates vendor scoring and pricing. | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 | Assumed
A-03 | Assumption | No items are blocked on other people | Digest reports zero items waiting on others — all open items require action from Corey Gray. | Corey Gray | If wrong, ownership needs reassignment. | Email — Daily Task Digest, 6 Sep 2026 | Assumed
A-04 | Assumption | User-generated content contest is still live | Initiative was assigned in Jan 2026 with no activity recorded since. | Corey Gray / Daichi Maruyama | Digest recommends confirming whether it is still active. | Teams — Marketing channel, 13 Jan 2026 | To confirm
I-01 | Issue | CloudFirst ERP fails mandatory requirements | Fails mandatory real-time processing and integration requirements and relies on future releases beyond the implementation window. | Corey Gray (Procurement Lead) | Recommended for disqualification; formal confirmation outstanding (A-11). | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 | Open
I-02 | Issue | Missing vendor data in proposals | Pricing, SLA and Compliance sheets were not retrievable for any vendor; no CSR/ESG data or customer references. | Corey Gray | Budget compliance unknown, operational risk unquantified, legal risk unresolved. | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 ("Data Gaps Summary") | Open
I-03 | Issue | ZAG-5 overdue | Jira item ZAG-5 (draft compliance criteria for agent behaviour) is reported overdue; ZAG-6 remains unassigned. | Corey Gray | Delays ZAVA AI Governance workstream. | Email — Jira digests, Aug-Sep 2026 | Open
I-04 | Issue | Both data connectors degraded at once | ServiceNow and Jira connectors are both flagged, within nine days of each other. | Corey Gray | Combined effect on task and ticket visibility. | Email — connector alerts, 12 and 21 Aug 2026 | Open
D-01 | Dependency | Executive budget decision (internal) | Contract negotiation cannot commence until the budget mitigation option is approved. | Executive Sponsor / Finance Director | Gates A-10 and the Week 2 negotiation start. | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 | Pending
D-02 | Dependency | Vendor clarification responses (external) | ERPMax and IntegraPro must return pricing/TCO, SLA with penalties, GDPR/ISO 27001/SOC 2 evidence and EMEA data-centre locations. | ERPMax Solutions; IntegraPro Systems | Gates final award; no response date stated in source. | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 | Pending — no date on record
D-03 | Dependency | Multi-party approval sign-off (internal) | Approval required from Corey Gray (Procurement Lead), Finance Director, Legal Counsel, CISO and Executive Sponsor. | Named approvers above | All five must sign before award. | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 | Pending
D-04 | Dependency | Azure OpenAI Assistants API retirement — 26 August 2026 (external, validated) | Vendor retirement date requiring transition to Microsoft Foundry Agent Service. Externally validated via web search: Microsoft Learn Q&A threads and industry coverage (windowsforum.com, ecorpit.com) all confirm 26 August 2026. | Corey Gray / owning engineering team | Date has already passed as of 7 Sep 2026 — verify no workload still depends on the retired API. Drives action A-19. | Email — retirement notice, 19 Aug 2026 + web validation | Overdue — verify
D-05 | Dependency | SAP/ARIBA approval workflow initialisation (internal) | Approval workflow in SAP/ARIBA to be initialised once vendor decisions are confirmed. | Procurement / Corey Gray | Downstream of D-01 and D-03. | Teams — Cloud ERP vendor offer analysis, 26 Feb 2026 | Not started

## Sources
Source | Type | Date | Used for
Daily Task Digest – Sunday, September 6, 2026 | Email (self-generated digest) | 2026-09-06 | Actions A-01 to A-07, A-09, A-13 to A-18; Risks R-02, R-03, R-05
Daily Task Digest – Friday, September 4, 2026 | Email | 2026-09-04 | Corroborates overdue items
Corey Gray, here is your weekly update for 2 Sept (Jira) | Email | 2026-09-02 | ZAG-6 unassigned (A-08)
1 of your flow(s) have failed / Alert! We've disabled one of your flows | Email (Power Automate) | 2026-08-31 / 2026-08-23 | A-13, R-04
Retirement notice: Transition Azure OpenAI Assistants APIs to Microsoft Foundry Agent Service by 26 August 2026 | Email | 2026-08-19 | A-19, D-04
Your Copilot connection ServiceNowTickets2607141032 needs immediate attention | Email | 2026-08-22 | A-04, R-02
Cloud ERP vendor offer analysis (RFP-2026-001) — Teams chat | Teams chat | 2026-02-26 | A-10 to A-12; R-01, R-06; assumptions; issues I-01, I-02; dependencies D-01 to D-03, D-05
Web search: Azure OpenAI Assistants API retirement (Microsoft Learn Q&A; windowsforum.com; ecorpit.com) | Web | Retrieved 2026-09-07 | External validation of the 26 Aug 2026 retirement date (D-04)
Meeting transcripts | Teams meetings | Searched 2026-08-08 to 2026-09-07 | No transcripts available in the period — no actions sourced from meetings