## Slide 1
CAMPAIGN READOUT · 1 OF 5 · RESULTS VS GOALS
Six plan targets are defined; no actual results have been reported in M365 yet
Goal (plan) | Target | Actual
Social media engagement | +25% in 6 months | Not reported
Website traffic | +30% in the quarter | Not reported
Website conversion rate | +15% in 6 months | Not reported
Online brand reputation | 4.5/5 rating; ≥80% positive sentiment | Not reported
New-segment reach | 10,000 potential clients in 3 months | Not reported
Online ad ROI | +20% conversions; −15% CPA in 6 months | Not reported
WHERE WE STAND
Targets come from the Contoso Marketing Plan (OneDrive).
No campaign results, dashboards or readouts were found in email, Teams, meetings or files.
Actuals must be added before this readout is signed off.
Sources: Contoso Marketing Plan.docx, section III; emails from Amrita Manik, 23 Mar 2026.
Notes: OWNER TO-DO: Fill the 'Actual' column with reported campaign results. No performance data, dashboards or readouts were found in email, Teams, meeting transcripts or files at the time this deck was built (3 Sep 2026). Targets are quoted from Contoso Marketing Plan.docx, section III 'Marketing Objectives'.

## Slide 2
CAMPAIGN READOUT · 2 OF 5 · WHAT WORKED
What worked: positioning got sharper, Legal caught risk early, sell-in assets shipped on plan
POSITIONING
LEGAL REVIEW
SELL-IN ASSETS
One differentiator, one persona
Risk flagged before launch
Kit shipped on schedule
Brief led with both 'speed' (2x faster) and 'intelligence'; sharpened to one differentiator and the VP of Operations persona.
Legal flagged the draft Nexara comparison chart early; revised language goes for sign-off before the one-pager is final.
ROI calculator beta and migration one-pager delivered on plan; enterprise customer quotes requested for the kit.
Source: email, Amrita Manik, 23 Mar 2026 — ZavaCore v2 Market Positioning
Source: email, Amrita Manik, 23 Mar 2026 — ZavaCore v2 Market Positioning
Source: email, Amrita Manik, 23 Mar 2026 — ROI Calculator Update
Common thread: decisions were forced early — before the agency started creative development.
Notes: Evidence: email from Amrita Manik (VP Marketing, Zava Technologies) to All-Company, 23 Mar 2026, 'ZavaCore v2 Market Positioning – Alignment Needed': differentiator speed vs intelligence, VP of Operations persona, Legal flagged the Nexara comparison chart. Email same date, 'Customer Sell-In Strategy – ROI Calculator Update': ROI calculator beta (inputs: workflow hours, users, error rate; output 12-month projected savings), migration one-pager drafted by Jordan Ellis, request for 2-3 enterprise customer quotes with Legal approval.

## Slide 3
CAMPAIGN READOUT · 3 OF 5 · COMPETITIVE & MARKET CONTEXT
Retail clicks cost $1.16 vs $2.96 cross-industry; 2026 winners lean on creators and retail media
Chart: 
| Restaurants & Food | Travel & Hospitality | Retail / eCommerce | Health & Wellness | Cross-Industry Average
Avg Google Search CPC 2026 (USD) | 1.84 | 1.63 | 1.16 | 1.08 | 2.96
CPC (USD): Restaurants 1.84 · Travel 1.63 · Retail/eCommerce 1.16 · Health 1.08 · Cross-industry 2.96 — Digital Applied, Google Ads Benchmarks 2026 (Apr 2026), citing WordStream Q1 2026.
Trends: retail media is now a core channel; many small creator activations beat one hero ad; ~30 test creatives a month outperform two films a quarter; incrementality replaces last-click — shopappy.com, 2026 retail campaign trends (Apr 2026).
Shoppers are value-led, trading down and waiting for promotions — dunnhumby US Consumer Trends Tracker (Feb 2026). Competitor plays: Aldi × Lewis Capaldi 'Cap-Aldi' rooftop gig; Heinz 'Looks Familiar' — StoryChief, 27+ Best Marketing Campaigns of 2026.
Notes: External benchmarks. CPC by industry: Digital Applied, 'Google Ads Benchmarks 2026: CPC, CTR, CVR by Industry' (5 Apr 2026), which cites WordStream Industry Benchmarks Q1 2026; cross-industry Search averages: CPC $2.96, CTR 3.52%, CVR 4.40%. Trends: shopappy.com, 'The 2026 retail campaign trends worth borrowing' (26 Apr 2026). Shopper behaviour: dunnhumby US Consumer Trends Tracker, Feb 2026. Campaign examples: StoryChief, '27+ Best Marketing Campaigns of 2026'. Chart is a native chart — edit data by right-clicking it.

## Slide 4
CAMPAIGN READOUT · 4 OF 5 · LEARNINGS
Learnings: measurement, decision speed and legal-ready assets will decide the next campaign
Measure from day one
Force choices early
Design legal-ready
Build for many surfaces
No results were reported in M365 against the plan's six targets. Agree dashboards and owners before the agency starts.
'Speed vs intelligence' and persona scope were still open after the kickoff call; lock them in the brief.
The Nexara comparison chart needed rework; pre-clear competitive claims and customer quotes with Legal.
2026 winners ran modular creative across retail media, creators and short video, not one hero ad (shopappy.com, Apr 2026).
Notes: Learnings synthesise the internal emails (positioning, legal review, sell-in assets), the absence of reported results in M365, and the shopappy.com 2026 trend review. Illustration is generated artwork, not a campaign asset.

## Slide 5
1
2
3
4
Lock the brief
Legal pre-clearance
Test creative fast
Measure real lift
Owner: Marketing. One differentiator, one persona, KPI targets and dashboards agreed before agency kickoff.
Owner: Legal + Marketing. Competitive claims (e.g. Nexara chart) and customer quotes cleared before creative starts.
Owner: Agency. Modular creative for retail media, creators and short video; scale winners with paid budget.
Owner: Analytics. Incrementality tests replace last-click; report plan targets vs actuals monthly.
CAMPAIGN READOUT · 5 OF 5 · NEXT CAMPAIGN PLAN
Next campaign: lock the brief, pre-clear claims, test creative fast, measure real lift
Ask: confirm the four owners and a results dashboard before the next agency kickoff.
Sources: Contoso Marketing Plan.docx; emails from Amrita Manik (23 Mar 2026); shopappy.com, 2026 retail campaign trends (Apr 2026); Digital Applied, Google Ads Benchmarks 2026 (Apr 2026).
Notes: OWNER TO-DO: confirm owners and target dates for each stage before presenting. Stages derive from the learnings slide; the '30 test creatives a month' and incrementality practices come from shopappy.com (Apr 2026).