## Slide 1
ZavaCore v2 beat its launch performance goals, but campaign outcomes were never measured
Load time 41% vs 35% target · Onboarding 4.3/5 vs 3.1/5 on v1 · Uptime 99.94% · API latency down 38%
Source: Beta Program Results, ZavaCore v2 Weeks 1-3, and R&D Quarterly Update, Damien Harbet. No post-launch campaign metrics found.
Chart: Percent improvement, and onboarding rating shown x10
| Load-time improvement (%) | Onboarding rating (x10)
Target / v1 baseline | 35 | 31
Beta actual | 41 | 43

## Slide 2
Product proof, sell-in tooling and CEO air cover carried the launch
PRODUCT
Performance proof
Load times improved 41% versus v1, beating the 35% launch target.
ENABLEMENT
Sell-in tooling
An ROI calculator and a migration one-pager were built for the sell-in kit.
LEADERSHIP
Exec air cover
The CEO note locked April 14 and mobilised every team behind it.
Product proof and sell-in tooling landed on time; positioning and legal approvals were the bottleneck.
Source: launch announcement (Nick Orford), beta results (Damien Harbet), sell-in strategy note (Amrita Manik), March 2026.

## Slide 3
Without our own funnel data, external 2026 benchmarks are the only yardstick we have
28-42%
B2B SaaS email open-rate range reported for 2026
3-7%
Click-through range for the same B2B programmes
1.8-4.5%
Reply-rate range across B2B email sequences
Our Nexara comparison chart is still held for legal sign-off, so competitive framing never reached launch assets.
External trackers also point to value-seeking, promotion-led buyer behaviour heading into 2026, favouring proof-of-savings messaging over feature claims.
Sources: Growthspree B2B SaaS email nurture benchmarks 2026; Stripo B2B open-rate research 2026; Deloitte ConsumerSignals and dunnhumby US Consumer Trends 2026.

## Slide 4
Every slip traced back to decisions left open, not to execution
1 Lock positioning earlier
Speed-versus-intelligence and the target persona were still unresolved as creative development began.
2 Route legal sooner
Both the competitor comparison chart and the customer quotes stalled waiting on sign-off.
3 Close integration gaps first
Intermittent Salesforce sync failures from beta were still open, with a fix only expected in RC2.
4 Instrument the campaign
No post-launch performance reporting exists in email, Teams, meetings or files to judge the campaign by.
Source: ZavaCore v2 positioning, sell-in and beta threads, March 2026; gaps confirmed by search across your email, Teams, meetings and files.

## Slide 5
Next campaign runs in four gated stages, with measurement built in from day one
1 POSITIONING
One claim, one
persona, signed off
2 APPROVALS
Legal clears claims
and quotes early
3 ASSETS
ROI tool and
one-pager shipped
4 MEASURE
Funnel tracked
weekly vs benchmark
Workstream | Owner | Status carried forward
Positioning sign-off | Amrita Manik | Open - speed vs intelligence
Competitive claims review | Legal | Open - Nexara comparison
Customer proof quotes | Amrita Manik | Open - 2 to 3 still needed
Integration fix | Damien Harbet | Salesforce sync, due in RC2
Source: ZavaCore v2 positioning and sell-in threads (Amrita Manik) and beta results (Damien Harbet), March 2026.