## 00_Project
PQD-FH 01 ¦ FQD editable templates
Project setup and appendix navigation
Project metadata | Enter once | Template control | Reference
Project / Facility |  | Template revision | 1.00
Project ID / Contract No. |  | Procedure revision | 1.00
Client / Owner |  | Release date | 2026-10-13T00:00:00.000Z
Contractor |  | Author | Arkadiusz Wójcik
Site / Location |  | License | CC BY-SA 4.0
Project workbook document ID
Project workbook revision |  | How to use
Project workbook status | Draft | 1. Complete the amber metadata fields. The appendix headers update automatically.
Prepared by
Reviewed by |  | 2. Define project requirements in A and register package IDs in B before completing related records.
Approved by
Project issue date |  | 3. Use dropdowns for controlled choices. Adapt project lists in Lists and project status names in H.
Reporting / review date
Required language(s) | English | 4. D1, F and G apply to the package selected in B10. Duplicate for another package or review. Archive an approved workbook version or fixed PDF; copied sheets retain live project metadata links.
Document-control procedure
5. Enter data in the prepared table rows. Use Tab in the last table cell to extend the table; copy a blank template row to carry dropdowns and formulas.
Worksheet | Purpose | 6. Amber cells are setup inputs. Blue text is editable content. Grey cells contain formulas. Red shading identifies entries to review.
A_Requirements | Editable register / reference table
B_Packages | Editable register / reference table | 7. Set the reporting date to evaluate overdue actions. Readiness and acceptance decisions require the authorized reviewer.
C_Deliverables | Editable register / reference table
D1_Package_Index | Editable register / reference table | 8. Preserve controlled records and project approvals. The public template contains no completed project records.
D2_Documents | Editable register / reference table
D3_Metadata | Editable register / reference table
D4_Classification | Editable register / reference table
E_Traceability | Editable register / reference table
F_Completion | Record counts, actions and completeness checks
G_Readiness | 22 criteria and recorded review decision
H_Status_Codes | Editable register / reference table
I_Responsibilities | Illustrative RACI with assignment checks
Lists | Project-adaptable choices
Source: PQD-FH 01 Universal FQD Procedure, Rev. 1.00, Appendices A-I.
Electronic implementation: combined fields are split for filtering; scope fields and local checks support use of the original tables.
Before use, adapt and identify this workbook as a controlled project document. Project requirements, record approvals and retention arrangements follow the applicable project procedures.
GitHub repository: arkadiuszwojcik-tech/PQD-FH
License: CC BY-SA 4.0

## A_Requirements
Appendix A - Project-specific requirements
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: | Project ID:
Client / Owner: | Contractor:
Project document ID: | Project revision:
Document status: Draft | Issue date:
Record the controlled project requirements and approval references. The universal procedure remains unchanged unless a formally controlled deviation is required.
Prepared by: | Reviewed by: / Approved by:
Project requirement | Value / Reference | Notes / Owner
Project / Facility
Client / Owner
Contractor
Applicable document control procedure
FQD numbering convention
FQD package breakdown rule
Required languages | English
CDE / EDMS
Required electronic formats
Hard-copy quantities
Hard-copy presentation requirements
Maximum volume / file size
Submission milestones and deadlines
Review / approval route
Required retention period
Red-Line / As-Built dossier rule
System Completion / Commissioning dossier interface
Project-specific RFI meaning / code
Project-specific WAP rule
Project-specific MCR rule
Mandatory package status codes
Mandatory index / template
Additional statutory / authority requirements
Applicable standards / editions and requirement references
Conditional readiness / acceptance authority and closure rules
Record custody, access, backup and migration requirements
Externally referenced records and receiving-party access
Changes after acceptance and resubmission rules
Document classification and project-code mapping
Asset identification scheme and cross-reference rules
Software and configuration handover scope

## B_Packages
Appendix B - FQD package register
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: |  |  |  | Project ID:
Client / Owner: |  |  |  | Contractor:
Project document ID: |  |  |  | Project revision:
Document status: Draft |  |  |  | Issue date:
Use unique package IDs. Record exclusions, shared records, boundary-document revisions and execution milestones or controlled schedule references in Interfaces / Notes.
Prepared by: |  |  |  | Reviewed by: / Approved by:
Package ID | Parent / System | Package title / Scope | Discipline / Area | Package owner | Planned completion | Planned submission | Status | Interfaces / Notes

## C_Deliverables
Appendix C - FQD deliverables matrix
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: |  |  |  |  | Project ID:
Client / Owner: |  |  |  |  | Contractor:
Project document ID: |  |  |  |  | Project revision:
Document status: Draft |  |  |  |  | Issue date:
One row per deliverable. Record its unique controlled reference and linked record IDs / revisions in Comment / N/A approval or a linked register (Section 7.2). Identify requirement revision and clause/activity. Record approved N/A dispositions.
Prepared by: |  |  |  |  | Reviewed by: / Approved by:
Package ID | Activity / Item | Requirement source | Acceptance criterion | Required record | ITP / ITPL / WAP ref. | Responsible party | Planned date | FQD section | Status | Comment / N/A approval

## D1_Package_Index
Appendix D.1 - Universal FQD package index
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: |  | Project ID:
Client / Owner: |  | Contractor:
Project document ID: |  | Project revision:
Document status: Draft |  | Issue date:
Select the package and milestone. Preserve generic applicability; record the project decision and any approved N/A justification in Project notes. Duplicate this sheet for each package.
Prepared by: |  | Reviewed by: / Approved by:
Package ID |  |  | Milestone / review ref.
No. | Section | Generic applicability | Project applicability | Project notes
00 | Cover and Identification | Required
01 | Document Control | Required
02 | FQD Index | Required
03 | Scope and Boundaries | Required
04 | Applicable Requirements | Required
05 | Quality Plan / ITP / ITPL / WAP | As applicable
06 | Approved Design Documents | As applicable
07 | Material / Equipment Register | As applicable
08 | Material / Product Compliance Records | As applicable
09 | Material / Equipment Traceability | As applicable
10 | Vendor Documentation | As applicable
11 | Personnel Qualifications | As applicable
12 | Inspection Records | As applicable
13 | Test Records | As applicable
14 | Calibration / Verification Records | As applicable
15 | NCR / Deviation Records | As applicable
16 | Punch / Open Points | As applicable
17 | Completion Records | As applicable
18 | Precommissioning / Commissioning Records | As applicable
19 | Red-Line / As-Built Reference | As applicable
20 | FQD Acceptance and Close-Out | Required
21 | Controlled Electronic FQD Package | Required

## D2_Documents
Appendix D.2 - Document register
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: |  |  |  | Project ID:
Client / Owner: |  |  |  | Contractor:
Project document ID: |  |  |  | Project revision:
Document status: Draft |  |  |  | Issue date:
List included and referenced controlled records at the required revision and status. Link D.3 using Document / Record ID plus revision. Preserve acceptance evidence in the controlled workflow.
Prepared by: |  |  |  | Reviewed by: / Approved by:
Package ID | FQD section | Document / Record ID | Title / Scope | Revision | Status | File / controlled location | Included / Referenced

## D3_Metadata
Appendix D.3 - Linked classification and scope metadata
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: |  |  | Project ID:
Client / Owner: |  |  | Contractor:
Project document ID: |  |  | Project revision:
Document status: Draft |  |  | Issue date:
Use the same document ID and revision as D.2. Keep multi-asset, multi-change and multi-package relationships controlled. Enter N/A when no change reference applies.
Prepared by: |  |  | Reviewed by: / Approved by:
Document / Record ID | Revision | Document type / Project code | Lifecycle stage | System / Asset / Scope | Change / RLM reference | Related package IDs

## D4_Classification
Appendix D.4 - Document classification and project mapping
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: |  | Project ID:
Client / Owner: |  | Contractor:
Project document ID: |  | Project revision:
Document status: Draft |  | Issue date:
Map the generic groups to approved project document types or codes. Typical sections are guidance; required records and acceptance criteria remain project-specific.
Prepared by: |  | Reviewed by: / Approved by:
Generic document group | Typical content | Typical FQD section | Project type / Code
Requirements and identification | Specifications; technical and identification standards; approved project requirements. | 04
Quality and execution planning | Quality plans; ITP/ITPL; work activity plans; method statements and inspection or test procedures. | 05
Design and engineering information | P&IDs; single-line, wiring and termination diagrams; layouts; equipment, cable, instrument and I/O lists; datasheets. | 06; 19 for final as-built references
Product conformity and traceability | Material compliance records; certificates; declarations; item, serial, batch or lot relationships. | 07–09
Manufacturing and factory evidence | Manufacturing dossier and index; factory inspection and test records; supplier conformity evidence. | 10; 08, 12 or 13 by record purpose
Installation evidence | Installation conformity dossier; field inspection records; installation checks and measurements. | 12–13; 17 for completion
Commissioning evidence | Pre-commissioning and functional test records; system verification and commissioning completion evidence. | 18; 17 for completion
Competence and measurement assurance | Personnel qualifications and authorizations; calibration or verification records. | 11; 14
Nonconformity and change control | NCR and concession records; punch closure; change approvals; RLM and as-built incorporation references. | 15–16; 19
Operation and maintenance information | Required supplier manuals, operating or maintenance instructions, spare-parts information and training records. | 10 or controlled handover reference
Software and configuration | Required native controller projects, source files, parameter sets and configuration manifests; readable programming documentation. | 21; linked design and test references
Package control and acceptance | Package and document indexes; boundary definitions; transmittals; review, completion and acceptance records. | 00–03; 17; 20–21

## E_Traceability
Appendix E - Material / equipment traceability
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: |  |  |  | Project ID:
Client / Owner: |  |  |  | Contractor:
Project document ID: |  |  |  | Project revision:
Document status: Draft |  |  |  | Issue date:
Use the required level of traceability. Include installed location where no unique tag exists. Keep additional certificate, revision and inspection references in linked controlled registers.
Prepared by: |  |  |  | Reviewed by: / Approved by:
No. | Installed ID / Tag | Description | Manufacturer | Type / Model | Batch / Lot / Heat / Drum / Serial | Certificate / MCR / Doc ID + Rev. | Inspection / Test ref. | Status

## F_Completion
Appendix F - FQD completion status register
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: | [5 empty] | Project ID:
Client / Owner: | [5 empty] | Contractor:
Project document ID: | [5 empty] | Project revision:
Document status: Draft | [5 empty] | Issue date:
Received, Reviewed and Accepted are cumulative counts of distinct records. Exclude superseded duplicates and conditional acceptance. Percentages require four valid whole-number counts and Expected > 0. Explain zero expected scope in H or use N with an approved N/A reference. Duplicate per package.
Prepared by: | [5 empty] | Reviewed by: / Approved by:
Package ID |  |  | Milestone / review ref.
No. | FQD section / Deliverable | Required Y / N | Expected records | Received | Reviewed | Accepted | Open comments / Action / N/A approval | Owner | Due date | Accepted / Expected | Count check

## G_Readiness
Appendix G - FQD package readiness checklist
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: |  |  | Project ID:
Client / Owner: |  |  | Contractor:
Project document ID: |  |  | Project revision:
Document status: Draft |  |  | Issue date:
Assess the applicable milestone. Record evidence, actions, owners and dates. Justify N/A and reference approval where required. Record the authorized readiness decision and conditions below and in the controlled package register.
Prepared by: |  |  | Reviewed by: / Approved by:
Package ID |  |  | Milestone / review ref.
No. | Readiness criterion | Yes / No / N/A | Evidence / Reference | Outstanding action / Conditions | Responsible party | Due date / Milestone
1 | Package scope and boundaries confirmed
2 | Package owner identified
3 | Deliverables matrix current
4 | Required ITP / ITPL / WAP records present
5 | Material / product compliance evidence complete
6 | Required traceability complete
7 | Inspection records completed, authenticated and at required status; inspection outcomes, actual inspected scope and links to subsequent inspections verified where applicable
8 | Test records completed, authenticated and at required status; results and referenced reports or attachments verified against the applicable acceptance criteria
9 | Calibration / verification valid at the test date; any known subsequent equipment deficiencies assessed for impact on the results, with required actions completed or formally dispositioned against the applicable milestone criteria (Section 11.3)
10 | Hold / witness point dispositions recorded
11 | NCR / deviation status acceptable
12 | Punch / open-point status acceptable for the milestone; required closure evidence verified; permitted residual items have assigned owners and agreed closure requirements and dates or milestones
13 | RLM / As-Built status and affected-document updates confirmed
14 | Completion / commissioning interface confirmed
15 | Revisions, authentication and approvals correct; required stamps and signatory identities, roles and authority verified
16 | Index matches package content
17 | Files readable, retrievable and correctly named; searchable where required
18 | Review comments dispositioned
19 | External references accessible to designated recipients
20 | Document types, lifecycle stages and asset / system links consistent
21 | Manufacturing, installation and commissioning evidence reconciled to the milestone
22 | Required software / configuration files match the accepted baseline
| Answered criteria | No responses | Readiness decision | Reviewed by | Review date | Decision / approval ref.
| 0 | 0 | Not reviewed
Authorized conditions / decision record
A count of Yes responses does not authorize submission or acceptance. Record permitted residual items, approval references and closure requirements. Preserve each completed package review as a controlled record.

## H_Status_Codes
Appendix H - Recommended FQD package status codes
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: |  | Project ID:
Client / Owner: |  | Contractor:
Project document ID: |  | Project revision:
Document status: Draft |  | Issue date:
Generic codes and meanings are retained in A-C. Adapt the project code and status in D-E to approved project rules; these status names feed the package dropdown in B.
Prepared by: |  | Reviewed by: / Approved by:
Generic code | Generic status | Generic meaning | Project code | Project status
PLN | Planned | Package defined but compilation not started. | PLN | Planned
IP | In Progress | Records are being generated and compiled. | IP | In Progress
IR | Internal Review | Package is undergoing internal completeness / conformity review. | IR | Internal Review
RFS | Ready for Submission | Internal readiness criteria satisfied. | RFS | Ready for Submission
SUB | Submitted | Formally transmitted for review / acceptance. | SUB | Submitted
UR | Under Review | Package is undergoing formal review by the designated reviewing authority. | UR | Under Review
CMT | Comment Resolution | Returned with review comments requiring action. | CMT | Comment Resolution
RSUB | Resubmitted | Reissued after comment resolution. | RSUB | Resubmitted
ACC | Accepted | Accepted by the designated reviewing authority to the required status. | ACC | Accepted
CLO | Closed | Package accepted and all required close-out actions completed. | CLO | Closed
HOLD | On Hold | Progress paused pending defined prerequisite, decision or corrective action. | HOLD | On Hold
CRDY | Conditionally Ready | Optional. Submission permitted by an authorized decision with identified residual items, owners and closure dates. | CRDY | Conditionally Ready
CACC | Conditionally Accepted | Optional. Accepted subject to recorded conditions, assigned owners and agreed closure dates; distinct from full acceptance. | CACC | Conditionally Accepted
REJ | Rejected / Revision Required | Optional. Acceptance criteria not met; corrective action and resubmission required. | REJ | Rejected / Revision Required

## I_Responsibilities
Appendix I - Example responsibility matrix
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: | [5 empty] | Project ID:
Client / Owner: | [5 empty] | Contractor:
Project document ID: | [5 empty] | Project revision:
Document status: Draft | [5 empty] | Issue date:
Illustrative assignments: adapt to the contract and approved project procedures. Assign one accountable role per activity and allocate work where several roles are responsible. R = responsible; A = accountable; C = consulted; I = informed.
Prepared by: | [5 empty] | Reviewed by: / Approved by:
Activity | Package owner | FQD coordinator | QA/QC | Construction | Commissioning | Document control | Contractor PM | Client / Owner | A count | R count | Assignment check
Define package scope | A | C | C | R | C | I | C | I | 1 | 1 | Assignments consistent
Define required records | A | R | R | C | C | I | C | I | 1 | 2 | Assignments consistent
Generate construction records | A | I | C | R | I | I | I | I | 1 | 1 | Assignments consistent
Generate commissioning records | A | I | C | C | R | I | I | I | 1 | 1 | Assignments consistent
Verify quality records | C | C | A/R | C | C | I | I | I | 1 | 1 | Assignments consistent
Maintain package register | A | R | C | I | I | C | I | I | 1 | 1 | Assignments consistent
Package readiness review | A | R | R | C | C | C | I | I | 1 | 2 | Assignments consistent
Formal submission | A | R | C | I | I | R | I | I | 1 | 2 | Assignments consistent
Resolve review comments | A | R | R | R | R | C | C | C | 1 | 4 | Assignments consistent
Final acceptance | I | I | C | I | I | C | C | A/R | 1 | 1 | Assignments consistent

## Lists
Project dropdown lists
PQD-FH 01 ¦ Editable templates 1.00 ¦ Procedure Rev. 1.00
Project: |  |  |  |  | Project ID:
Client / Owner: |  |  |  |  | Contractor:
Project document ID: |  |  |  |  | Project revision:
Document status: Draft |  |  |  |  | Issue date:
Adapt these options to approved project requirements. Keep entries contiguous within rows 13-52. Package statuses are maintained in H_Status_Codes.
Prepared by: |  |  |  |  | Reviewed by: / Approved by:
Disciplines | Record Statuses | Lifecycle Stages | Traceability Statuses | Inclusion Types | Applicability Choices | Required Choices | Readiness Responses | RACICodes | Document Statuses | Readiness Decisions
Electrical | Planned | Design / Engineering | Pending | Included | Required | Y | Yes | R | Draft | Not reviewed
Instrumentation & Control | In Preparation | Manufacturing / Factory | Under Review | Referenced | As applicable | N | No | A | Internal Review | Not ready
Mechanical | Internal Review | Delivery / Receipt | Verified |  | N/A |  | N/A | C | For Review | Ready for Submission
Civil / Structural | Ready for Submission | Installation / Construction | Accepted |  |  |  |  | I | For Approval | Conditionally Ready
Process | Submitted | Pre-commissioning | Conditionally Accepted |  |  |  |  | A/R | Approved
Piping | Under Review | Commissioning | Rejected | [5 empty] | Issued
HVAC | Comment Resolution | Acceptance / Handover | On Hold | [5 empty] | Superseded
Multidiscipline | Resubmitted | Operation / Maintenance | N/A
Other | Accepted
Closed
Conditionally Accepted
On Hold
Rejected / Revision Required
Superseded
N/A