## Gantt Chart
Project plan (Gantt chart) | [31 empty] | https://goo.gl/PXLbMe
| PROJECT | Barberotheca
| PROJECT MANAGER | Tommaso Barbato, Martina Uccheddu
[6 empty] | ITERATION 1 |  |  |  |  | ITERATION 2 | [6 empty] | ITERATION 3 | [8 empty] | ITERATION 4
WBS NUMBER | TASK TITLE | TASK OWNER | START DATE | DUE DATE | DURATION | WEEK 1 |  |  |  |  | WEEK 2 |  |  |  |  | WEEK 3 |  |  |  |  | WEEK 4 |  |  |  |  | WEEK 5 |  |  |  |  | WEEK 6
[6 empty] | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F | M | T | W | R | F
1 | Concept validation & basic MVP
1.1 | Identify sources | Domain Expert | 2026-02-02 | 2026-02-03 | 2 | bar: WEEK 1 M to WEEK 1 T
1.2 | Define metadata needed structure | Data Steward | 2026-02-02 | 2026-02-03 | 2 | bar: WEEK 1 M to WEEK 1 T
1.3 | Compile initial raw dataset | Data Steward | 2026-02-04 | 2026-02-06 | 3 | bar: WEEK 1 W to WEEK 1 F
1.4 | Define desired types and formats | Solution Architect | 2026-02-02 | 2026-02-02 | 1 | bar: WEEK 1 M
1.5 | Establish required tools | Solution Architect | 2026-02-03 | 2026-02-04 | 2 | bar: WEEK 1 T to WEEK 1 W
1.6 | Acquire audio files (I) | Solution Architect | 2026-02-05 | 2026-02-05 | 1 | bar: WEEK 1 R
1.7 | UX design and layout definition (I) | UX/UI | 2026-02-02 | 2026-02-03 | 2 | bar: WEEK 1 M to WEEK 1 T
1.8 | Media rendering component (I) | Web Developer | 2026-02-02 | 2026-02-03 | 2 | bar: WEEK 1 M to WEEK 1 T
2 | Pipeline structuring & basic automation
2.1 | Acquire audio files (II) | Solution Architect | 2026-02-09 | 2026-02-10 | 2 | bar: WEEK 2 M to WEEK 2 T
2.2 | Perform speech-to-text transcription (I) | Solution Architect | 2026-02-11 | 2026-02-13 | 3 | bar: WEEK 2 W to WEEK 2 F
2.3 | Harmonize semantic naming | Data Steward | 2026-02-10 | 2026-02-10 | 1 | bar: WEEK 2 T
2.4 | Extract keyword and entities (I) | Solution Architect | 2026-02-16 | 2026-02-17 | 2 | bar: WEEK 3 M to WEEK 3 T
2.5 | UX design and layout definition (II) | UX/UI | 2026-02-09 | 2026-02-10 | 2 | bar: WEEK 2 M to WEEK 2 T
2.6 | Data integration and logic (I) | Web Developer | 2026-02-09 | 2026-02-10 | 2 | bar: WEEK 2 M to WEEK 2 T
3 | Semantic enrichment & application growth
3.1 | Acquire audio files (III) | Solution Architect | 2026-02-11 | 2026-02-13 | 3 | bar: WEEK 3 W to WEEK 3 F
3.2 | Verify audio integrity | QA | 2026-02-13 | 2026-02-16 | 2 | bar: WEEK 3 F to WEEK 4 M
3.3 | Perform speech-to-text transcription (II) | Solution Architect | 2026-02-16 | 2026-02-18 | 3 | bar: WEEK 4 M to WEEK 4 W
3.4 | Review transcription quality | Domain Expert | 2026-02-11 | 2026-02-13 | 3 | bar: WEEK 3 W to WEEK 3 F
3.5 | Media rendering component (II) | Web Developer | 2026-02-11 | 2026-02-13 | 3 | bar: WEEK 3 W to WEEK 3 F
3.6 | Data integration and logic (II) | Web Developer | 2026-02-16 | 2026-02-18 | 3 | bar: WEEK 4 M to WEEK 4 W
3.7 | UX design and layout definition (III) | UX/UI | 2026-02-11 | 2026-02-12 | 2 | bar: WEEK 3 W to WEEK 3 R
3.8 | Extract keyword and entities (II) | Solution Architect | 2026-02-19 | 2026-02-23 | 3 | bar: WEEK 4 R to WEEK 5 M
3.9 | Reconcile authority controlled entities | Domain Expert | 2026-02-19 | 2026-02-23 | 3 | bar: WEEK 4 R to WEEK 5 M
4 | Finalization, documentation, validation
4.1 | Review automated metadata extraction | QA | 2026-02-24 | 2026-02-25 | 2 | bar: WEEK 5 T to WEEK 5 W
4.2 | Optimize data for storage | Solution Architect | 2026-02-24 | 2026-02-25 | 2 | bar: WEEK 5 T to WEEK 5 W
4.3 | Research further concepts connections | Domain Expert | 2026-02-24 | 2026-02-25 | 2 | bar: WEEK 5 T to WEEK 5 W
4.4 | Review authority control connections | Domain Expert | 2026-02-26 | 2026-02-27 | 2 | bar: WEEK 5 R to WEEK 5 F
4.5 | Provide format convertibility | Solution Architect | 2026-02-26 | 2026-02-26 | 1 | bar: WEEK 5 R
4.6 | Produce final data assets for publication | Solution Architect | 2026-02-27 | 2026-02-27 | 1 | bar: WEEK 5 F
4.7 | User testing | UX/UI | 2026-02-24 | 2026-02-25 | 2 | bar: WEEK 5 T to WEEK 5 W
4.8 | Document audio ingestion steps | Data Steward | 2026-02-24 | 2026-02-24 | 1 | bar: WEEK 5 T
4.9 | Document transcription workflow | Data Steward | 2026-02-25 | 2026-02-25 | 1 | bar: WEEK 5 W
0.17361 | Document metadata production | Data Steward | 2026-02-26 | 2026-02-26 | 1 | bar: WEEK 5 R
0.17431 | Test-drive the guide | QA | 2026-02-26 | 2026-02-26 | 1 | bar: WEEK 5 R
0.175 | Select critical function/feature | Web Developer | 2026-02-24 | 2026-02-24 | 1 | bar: WEEK 5 T
0.17569 | Define document template | UX/UI | 2026-02-26 | 2026-02-26 | 1 | bar: WEEK 5 R
0.17639 | Draft instructions | UX/UI | 2026-02-27 | 2026-02-27 | 1 | bar: WEEK 5 F
0.17708 | Check accuracy | QA | 2026-02-27 | 2026-02-27 | 1 | bar: WEEK 5 F
0.17847 | Editorial review | QA | 2026-03-02 | 2026-03-03 | 2 | bar: WEEK 6 M to WEEK 6 T
EST. TOTAL EFFORT = 27 days